## README
Audit-Evidence Tracker (PBC)
Wrenfield Health (fictional) · simulated NIST SP 800-53 Rev. 5 (Release 5.2.0) assessment · synthetic data
As-of (status) date | 2026-09-18 | <- input: all aging/overdue formulas reference this cell (use =TODAY() in a live workbook)
Statuses | Not Requested, Requested, Received, Under Review, Accepted, Insufficient, Rework Required, Closed
Evidence level | Design = documentation exists; Implementation = configured/deployed; Operating Effectiveness = worked over the period. See audit/evidence-quality-guide.md
Sufficiency | Derived: Accepted/Closed = Sufficient; Insufficient/Rework = Insufficient; others Pending
Days Late | Live formula: received after due, or still outstanding past due as of the README date
Completion % | (Accepted + Closed) / all requested items. 'Insufficient' is NOT complete: it becomes a finding
Locations | Paths starting with evidence/ or access-review/ are synthetic samples committed in this repo; 'GRC-Vault:/' paths are the fictional evidence vault

## Evidence
Evidence ID | Control ID | Evidence Request | Artifact Description | Evidence Owner | Request Date | Due Date | Received Date | Status | Evidence Period | File / Repository Location | In Repo? | Reviewer | Review Result | Evidence Level | Sufficiency | Exception | Follow-Up Required | Days Late | Notes
EVID-001 | AC-1 | Current Access Control Policy with approval record and review history | ACP-002 Access Control Policy v3.1 (PDF) + approval minutes 2025-01-15 | Alicia Moreno | 2026-06-10 | 2026-06-19 | 2026-06-12 | Accepted | Current version | GRC-Vault:/WCP-2026/AC/EVID-001_ACP-002_v3.1.pdf | No | Lead assessor | Content adequate; last approval 2025-01-15 exceeds the annual review cycle | Design | Sufficient |  | No |  | Drives OBS-01. Policy existence alone did not satisfy AC-2 or AC-6
EVID-002 | AC-2; AC-2(3); PS-4; PS-5 | Joiner/mover/leaver procedure | SOP-IAM-02 Account Lifecycle v2.0 | Nadia Rahman | 2026-06-10 | 2026-06-19 | 2026-06-12 | Accepted | Current version | GRC-Vault:/WCP-2026/AC/EVID-002_SOP-IAM-02_v2.0.pdf | No | Lead assessor | Describes a manual HR-email to IT-ticket flow; no step for local accounts or transfers | Design | Sufficient |  | No |  | Design gap is visible in the procedure itself
EVID-003 | AC-2(3); PS-4 | System-generated list of ALL terminations 2026-01-01 to 2026-06-30 (worker ID, type, date, effective time) | PeopleHub report 'Terminations by Effective Date' + final-pay reconciliation | Denise Yamamoto | 2026-06-10 | 2026-06-19 | 2026-06-17 | Accepted | 2026-01-01 to 2026-06-30 | evidence/AC/EVID-003_peoplehub-terminations-2026H1.csv | Yes | Lead assessor | IPE validated: 19 of 19 reconciled to final pay/invoice | Operating Effectiveness | Sufficient |  | No |  | Assessor observed report generation over screen share
EVID-004 | AC-2(3) | Okta System Log export of user.lifecycle.deactivate events for the period | Okta System Log API export | Nadia Rahman | 2026-06-10 | 2026-06-19 | 2026-06-17 | Accepted | 2026-01-01 to 2026-06-30 | evidence/AC/EVID-004_okta-deactivation-events-2026H1.csv | Yes | Lead assessor | 17 events; matched to EVID-003 | Operating Effectiveness | Sufficient |  | No
EVID-005 | AC-2; AC-2(1); IA-2; AC-6(2) | Okta user export (all statuses) with MFA enrollment and group membership as of 2026-06-30 | Okta Users API export | Nadia Rahman | 2026-06-10 | 2026-06-19 | 2026-07-01 | Accepted | As of 2026-06-30 | access-review/source-exports/okta_users.csv | Yes | Lead assessor | Complete for in-scope population; account types verified | Implementation | Sufficient |  | No
EVID-006 | AC-2; AC-6; AC-6(5) | Entitlement exports from each in-scope system as of 2026-06-30 | Exports from AWS IAM Identity Center/IAM, GitHub, Aurora roles, wf-sftp-01, PeopleHub, Ledgerline, SIEM, EDR, Quarrystone portal | System owners (9 systems) | 2026-06-10 | 2026-07-01 | 2026-07-03 | Accepted | As of 2026-06-30 | access-review/source-exports/entitlements.csv | Yes | Lead assessor | 106 entitlements; 2 exports re-pulled after column omissions (Ledgerline, portal) | Implementation | Sufficient |  | No |  | Ledgerline export first omitted role assignment dates; returned 2026-07-03
EVID-007 | AC-2; IA-2(1); IA-5 | AWS IAM credential report for wcp-prod | IAM credential report (CSV) | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-07-01 | Accepted | As of 2026-06-30 | evidence/IA/EVID-007_aws-iam-credential-report_2026-06-30.csv | Yes | Lead assessor | Revealed mfeld-admin (no MFA) and svc-reporting-etl static key | Implementation | Sufficient |  | No
EVID-008 | AC-6(7) | Q1 2026 access certification campaign export (reviewer, item, decision, timestamp) | Okta Access Certification campaign export Q1-2026 (412 decisions) | Alicia Moreno | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | 2026-03-02 to 2026-03-20 | evidence/AC/EVID-008_q1-certification-summary.md | Yes | Lead assessor | 100% approved; 17 of 23 reviewers finished in under 5 minutes; approved 2 items later found invalid | Operating Effectiveness | Sufficient |  | No
EVID-009 | AC-6(7) | Evidence that quarterly access reviews are performed | Screenshot: 'Q1 Access Review, 100% complete' dashboard tile | Alicia Moreno | 2026-06-10 | 2026-06-19 | 2026-06-15 | Insufficient | Undated | evidence/AC/EVID-009_insufficient-screenshot-example.md | Yes | Lead assessor | No population, reviewers, decisions, or date; cannot show review quality | Design | Insufficient | Screenshot shows completion status only | Yes: replaced by EVID-008 |  | Teaching example: completion does not prove effectiveness
EVID-010 | IA-2(1); IA-2(2); IA-2(8) | Okta authentication and global session policy export | Okta Policies API export | Nadia Rahman | 2026-06-10 | 2026-06-19 | 2026-06-30 | Accepted | As of 2026-06-30 | evidence/IA/EVID-010_okta-authentication-policies_2026-06-30.json | Yes | Lead assessor | Global policy excludes MFA-Exempt-Legacy group; admin apps accept non-phishing-resistant factors | Implementation | Sufficient |  | No
EVID-011 | IA-2(1); IA-2(2) | Membership of all MFA exemption groups with reason and approval | Okta group membership export MFA-Exempt-Legacy | Nadia Rahman | 2026-06-10 | 2026-06-19 | 2026-06-30 | Accepted | As of 2026-06-30 | evidence/IA/EVID-011_okta-mfa-exempt-group_2026-06-30.csv | Yes | Lead assessor | 11 members (9 human, 2 service); 0 approvals or expiry dates | Implementation | Sufficient |  | No
EVID-012 | IA-2(8) | Enabled authenticator configuration | Okta authenticator settings export | Nadia Rahman | 2026-06-10 | 2026-06-19 | 2026-06-30 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/IA/EVID-012_okta-authenticators.json | No | Lead assessor | Only replay-resistant factors enabled; SMS/voice disabled | Implementation | Sufficient |  | No
EVID-013 | AC-2; IA-5 | Service-account register with owner, purpose, credential type, and last rotation | Service account register v2026-06 | Nadia Rahman | 2026-06-10 | 2026-06-26 | 2026-07-08 | Accepted | As of 2026-06-30 | access-review/source-exports/service_accounts.csv | Yes | Lead assessor | Accepted after rework | Implementation | Sufficient |  | No |  | First submission (2026-06-25) lacked owner and rotation columns; returned as Rework Required; accepted 2026-07-08
EVID-014 | AC-5 | Ledgerline role and permission matrix and SoD ruleset | Ledgerline security role report + SoD matrix | Laura Brenneman | 2026-06-10 | 2026-06-19 | 2026-06-18 | Accepted | Current | access-review/source-exports/sod_rules.csv | Yes | Lead assessor | Rules adequate; conflict detected in assignments | Design | Sufficient |  | No
EVID-015 | AC-5 | Monthly vendor-master change reports with reviewer sign-off (Jan–Jun) | 6 signed Ledgerline vendor-master change reports | Laura Brenneman | 2026-06-10 | 2026-06-19 | 2026-06-22 | Accepted | 2026-01 to 2026-06 | GRC-Vault:/WCP-2026/AC/EVID-015_vendor-master-reviews-H1.pdf | No | Lead assessor | 6 of 6 signed by Controller within 10 days of month end; 2 bank-detail changes verified by callback | Operating Effectiveness | Sufficient |  | No
EVID-016 | AC-6; AC-6(2); AC-6(5) | AWS IAM Identity Center permission-set assignments for wcp-prod | Identity Center assignment export | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-07-01 | Accepted | As of 2026-06-30 | access-review/source-exports/entitlements.csv | Yes | Lead assessor | Admin assignments exceed role definitions | Implementation | Sufficient |  | No
EVID-017 | AC-6(5) | GitHub organization owners and repository admins | GitHub org member export (role=owner/admin) | Grace Lindqvist | 2026-06-10 | 2026-06-19 | 2026-07-01 | Accepted | As of 2026-06-30 | access-review/source-exports/entitlements.csv | Yes | Lead assessor | 5 owners vs maximum 3 | Implementation | Sufficient |  | No
EVID-018 | AC-17 | Remote administrative access architecture and session logging configuration | SSM Session Manager preferences + network exposure report | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/AC/EVID-018_ssm-session-prefs.json | No | Lead assessor | Sessions logged and encrypted; no public bastions | Implementation | Sufficient |  | No
EVID-019 | AT-2 | LMS completion report for annual security awareness (full workforce) and phishing simulation results | LMS report + simulation summary | Denise Yamamoto | 2026-06-10 | 2026-06-19 | 2026-06-26 | Accepted | FY2026 cycle as of 2026-06-30 | GRC-Vault:/WCP-2026/AT/EVID-019_lms-completion-2026-06-30.csv | No | Lead assessor | 316 of 347 complete (91%); 4 overdue users hold PHI access | Operating Effectiveness | Sufficient |  | No
EVID-020 | AT-3 | Role-based training completion for engineers, admins, clinical/support staff | LMS role-group reports | Denise Yamamoto | 2026-06-10 | 2026-06-19 | 2026-06-26 | Accepted | 2026-01-01 to 2026-06-30 | GRC-Vault:/WCP-2026/AT/EVID-020_role-training.csv | No | Lead assessor | 15 of 15 sampled complete | Operating Effectiveness | Sufficient |  | No
EVID-021 | AU-2 | Logging standard, trail configurations, and sample events for required types | LMS-004 + CloudTrail/EKS/app-audit configs + 10 traced events | Owen Castillo | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/AU/EVID-021_logging-config-and-samples.zip | No | Lead assessor | 10 of 10 required event types present with required fields | Implementation | Sufficient |  | No
EVID-022 | AU-6 | All weekly privileged-activity review tickets W01–W26 | SEC ticket export | Owen Castillo | 2026-06-10 | 2026-06-19 | 2026-06-26 | Accepted | 2026-W01 to 2026-W26 | evidence/AU/EVID-022_privileged-activity-reviews-2026H1.csv | Yes | Lead assessor | 19 of 26 performed; 17 of 26 fully effective | Operating Effectiveness | Sufficient |  | No
EVID-023 | AU-9 | Log archive bucket protections and SCPs | S3 Object Lock config + bucket policy + SCP JSON | Owen Castillo | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/AU/EVID-023_log-archive-protections.json | No | Lead assessor | Compliance-mode Object Lock; StopLogging denied | Implementation | Sufficient |  | No
EVID-024 | AU-11 | Retention settings for every audit source plus oldest available record per source | SIEM retention setting + S3 lifecycle + CloudWatch retention + oldest-record queries | Owen Castillo | 2026-06-10 | 2026-06-19 | 2026-06-25 | Accepted | As of 2026-06-30 | evidence/AU/EVID-024_log-retention-config_2026-06-30.json | Yes | Lead assessor | Retention 90–180 days vs 12-month requirement | Implementation | Sufficient |  | No
EVID-025 | CA-2 | Most recent SOC 2 Type II report and external penetration test report | SOC 2 Type II (2024-10-01 to 2025-09-30) + 2025 pentest summary and retest letter | Priya Raman | 2026-06-10 | 2026-06-19 | 2026-06-12 | Accepted | FY2025 | GRC-Vault:/WCP-2026/CA/EVID-025_soc2-and-pentest.pdf | No | Lead assessor | Independent assessments at defined frequency | Operating Effectiveness | Sufficient |  | No
EVID-026 | CA-3; SA-9 | Quarrystone MSA/BAA and data sharing specification; 3 customer interface specs | Contracts + Data Sharing Specification v2 + 3 interface specs | Liam Porter | 2026-06-10 | 2026-06-19 | 2026-06-19 | Accepted | Current | GRC-Vault:/WCP-2026/CA/EVID-026_interconnection-agreements.zip | No | Lead assessor | Agreements present; Quarrystone terms inadequate (see VR-002/005) | Design | Sufficient |  | No
EVID-027 | CA-5; RA-7 | Existing security issue tracking (pre-assessment) | Jira SECISSUE export (37 items) | Priya Raman | 2026-06-10 | 2026-06-19 | 2026-06-15 | Accepted | 2025-07-01 to 2026-06-30 | GRC-Vault:/WCP-2026/CA/EVID-027_secissue-export.csv | No | Lead assessor | 100% with owner and due date; 4 overdue | Operating Effectiveness | Sufficient |  | No
EVID-028 | CM-6; CA-7; SC-7; AC-17 | Security Hub CIS benchmark results and finding history | Security Hub summary + finding history export | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | 2026-01-01 to 2026-06-30 | GRC-Vault:/WCP-2026/CM/EVID-028_securityhub.csv | No | Lead assessor | 97% passing; 3 High findings untriaged > 30 days | Implementation | Sufficient |  | No
EVID-029 | CM-2 | Terraform baseline and AMI build specification; drift check output | Repo links + AMI pipeline spec + drift plan output (3 modules) | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/CM/EVID-029_baseline.zip | No | Lead assessor | No drift in sampled modules | Implementation | Sufficient |  | No
EVID-030 | CM-3 | Population of production changes (212) and full records for the 25 sampled (seed 20260618) | Jira CHG export + PR/deploy records | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-29 | Accepted | 2026-01-01 to 2026-06-30 | evidence/CM/EVID-030_change-sample-2026H1.csv | Yes | Lead assessor | 3 of 25 exceptions | Operating Effectiveness | Sufficient |  | No
EVID-031 | CM-8; RA-5 | Asset inventory (AWS Config aggregator + MDM) with tag compliance | Config resource inventory + MDM export + tag-compliance report | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/CM/EVID-031_inventory.zip | No | Lead assessor | Complete; 93% owner-tag compliance | Implementation | Sufficient |  | No
EVID-032 | CP-2 | Current BC/DR plan | BCP-003 v2.1 (2025-11) | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-12 | Accepted | Current version | GRC-Vault:/WCP-2026/CP/EVID-032_BCP-003_v2.1.pdf | No | Lead assessor | Adequate design with RTO 4h / RPO 1h | Design | Sufficient |  | No
EVID-033 | CP-4 | Contingency plan test records (last 24 months) | 2024-04 AZ failover engineering notes | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-26 | Insufficient | 2024-07-01 to 2026-06-30 | GRC-Vault:/WCP-2026/CP/EVID-033_az-failover-notes-2024.md | No | Lead assessor | No plan-level test within 12 months; notes are not an after-action report | Design | Insufficient | No CP test in period | Yes: POAM-014
EVID-034 | CP-9 | Backup plans, job history (30 days), vault protections | AWS Backup plan JSON + job history + Vault Lock config | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | 2026-06-01 to 2026-06-30 | GRC-Vault:/WCP-2026/CP/EVID-034_backup-config.zip | No | Lead assessor | 30 of 30 jobs successful; Vault Lock compliance mode | Operating Effectiveness | Sufficient |  | No
EVID-035 | CP-9(1) | Backup restore test records | Backup job success notifications (no restore records) | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-26 | Insufficient | 2025-07-01 to 2026-06-30 | GRC-Vault:/WCP-2026/CP/EVID-035_backup-job-notifications.pdf | No | Lead assessor | A successful backup job is not a tested restore | Implementation | Insufficient | No restore test ever documented | Yes: POAM-013
EVID-036 | IR-8 | Current incident response plan with review history | IRP-005 v4.0 (reviewed 2025-11) | Owen Castillo | 2026-06-10 | 2026-06-19 | 2026-06-12 | Accepted | Current version | GRC-Vault:/WCP-2026/IR/EVID-036_IRP-005_v4.0.pdf | No | Lead assessor | Current; stale contact roster (OBS-03) | Design | Sufficient |  | No
EVID-037 | IR-3 | IR test/exercise records (last 24 months) | 2024-09-18 tabletop after-action report | Owen Castillo | 2026-06-10 | 2026-06-19 | 2026-06-26 | Insufficient | 2024-07-01 to 2026-06-30 | GRC-Vault:/WCP-2026/IR/EVID-037_tabletop-2024-09.pdf | No | Lead assessor | Most recent exercise 21 months before fieldwork | Design | Insufficient | No IR test in 12 months | Yes: POAM-014
EVID-038 | IR-4; IR-6; SI-3 | All incident tickets for the period with timelines and notifications | Incident register export (6 incidents) | Owen Castillo | 2026-06-10 | 2026-06-19 | 2026-06-26 | Accepted | 2026-01-01 to 2026-06-30 | evidence/IR/EVID-038_incident-tickets-2026H1.csv | Yes | Lead assessor | 6 of 6 handled per plan; notification timely | Operating Effectiveness | Sufficient |  | No
EVID-039 | MP-6 | Certificates of destruction for all devices retired in the period | 14 Coldwater certificates + MDM retired-device list | Kevin Brandt | 2026-06-10 | 2026-06-19 | 2026-06-22 | Accepted | 2026-01-01 to 2026-06-30 | GRC-Vault:/WCP-2026/MP/EVID-039_itad-certificates.pdf | No | Lead assessor | 14 of 14 reconciled by serial | Operating Effectiveness | Sufficient |  | No
EVID-040 | PE-3; MP-6; AC-18 | Inherited-control record and provider attestation review log; boundary definition | Control inheritance record + 2026-03 attestation review note + boundary diagram | Priya Raman | 2026-06-10 | 2026-06-19 | 2026-06-15 | Accepted | Current | docs/scope/system-profile.md | Yes | Lead assessor | Inheritance documented and reviewed | Design | Sufficient |  | No
EVID-041 | PL-2 | Current system security plan | SSP v1.3 (2025-02) | Priya Raman | 2026-06-10 | 2026-06-19 | 2026-06-12 | Accepted | Current version | GRC-Vault:/WCP-2026/PL/EVID-041_SSP_v1.3.pdf | No | Lead assessor | Outdated: 3 architecture changes missing; 27 of 61 controls overstated vs testing | Design | Sufficient |  | No
EVID-042 | PM-9 | Risk management strategy and Board-approved risk appetite | RMS-001 + Risk Appetite Statement (Board minutes 2025-10-21) | Alicia Moreno | 2026-06-10 | 2026-06-19 | 2026-06-12 | Accepted | Current | GRC-Vault:/WCP-2026/PM/EVID-042_RMS-001_and_appetite.pdf | No | Lead assessor | Adequate; applied in RACC-001 and VR-001 escalation | Design | Sufficient |  | No
EVID-043 | PS-3 | Background-check completion for 15 sampled H1 hires/contractors | Screening vendor reports + Northgate attestations | Denise Yamamoto | 2026-06-10 | 2026-06-19 | 2026-06-22 | Accepted | 2026-01-01 to 2026-06-30 | GRC-Vault:/WCP-2026/PS/EVID-043_screening-sample.pdf | No | Lead assessor | 15 of 15 screened before access | Operating Effectiveness | Sufficient |  | No
EVID-044 | PS-5 | All transfers in period with before/after access | PeopleHub transfer report (6) + access tickets | Denise Yamamoto | 2026-06-10 | 2026-06-19 | 2026-06-22 | Accepted | 2026-01-01 to 2026-06-30 | GRC-Vault:/WCP-2026/PS/EVID-044_transfers.csv | No | Lead assessor | 1 of 6 retained prior-role PHI access | Operating Effectiveness | Sufficient |  | No
EVID-045 | PS-7 | Contractor roster with SOW start/end dates and scope | Northgate SOW register (5 contractors active in H1) | Sofia Ricci | 2026-06-10 | 2026-06-19 | 2026-06-22 | Accepted | 2026-01-01 to 2026-06-30 | GRC-Vault:/WCP-2026/PS/EVID-045_contractor-sow-register.xlsx | No | Lead assessor | End dates not enforced in Okta; scope not mapped to access | Implementation | Sufficient |  | No
EVID-046 | RA-2 | FIPS 199 categorization worksheet with approval | Categorization worksheet (2025-06) | Samir Haddad | 2026-06-10 | 2026-06-19 | 2026-06-12 | Accepted | Current | docs/scope/system-profile.md | Yes | Lead assessor | Moderate categorization confirmed | Design | Sufficient |  | No
EVID-047 | RA-3 | Most recent risk assessment | 2025 HIPAA risk analysis report (2025-09) | Priya Raman | 2026-06-10 | 2026-06-19 | 2026-06-12 | Accepted | FY2025 | GRC-Vault:/WCP-2026/RA/EVID-047_risk-analysis-2025.pdf | No | Lead assessor | Adequate method; missed vendor offshore and retention risks | Design | Sufficient |  | No
EVID-048 | RA-5; SI-2; SA-22 | All Critical/High vulnerability findings open at any point in H1, with detection and remediation dates | Scanner export (61 findings) | Owen Castillo | 2026-06-10 | 2026-06-19 | 2026-06-29 | Accepted | 2026-01-01 to 2026-06-30 | evidence/RA/EVID-048_vuln-remediation-aging-2026H1.csv | Yes | Lead assessor | 14 of 61 beyond SLA; 6 open past SLA | Operating Effectiveness | Sufficient |  | No
EVID-049 | SA-9; SR-6 | Vendor inventory with tiers and assessment dates | Vendor register (16 vendors) | Beth Kowalski | 2026-06-10 | 2026-06-19 | 2026-06-19 | Accepted | As of 2026-06-30 | vendor-risk/vendor-assessment.xlsx | Yes | Lead assessor | 5 of 14 Tier 1–2 vendors overdue or never assessed | Implementation | Sufficient |  | No
EVID-050 | SR-6; SA-9 | Quarrystone SOC 2 Type II report and bridge letter | Quarrystone SOC 2 Type II (2024-10-01 to 2025-09-30) + bridge letter to 2026-03-31 | Beth Kowalski | 2026-06-10 | 2026-06-19 | 2026-06-30 | Accepted | 2024-10-01 to 2026-03-31 | evidence/SR/EVID-050_quarrystone-soc2-review-workpaper.md | Yes | Lead assessor | Unqualified; 2 exceptions; subservice carve-outs; CUEC not performed by Wrenfield | Operating Effectiveness | Sufficient |  | No
EVID-051 | SR-6 | Quarrystone most recent penetration test report and retest evidence | Summary letter only (2025-03 test); full report and retest requested | Beth Kowalski (vendor-sourced) | 2026-07-08 | 2026-08-07 |  | Requested | 2025-03 | GRC-Vault:/WCP-2026/SR/EVID-051_pending | No | Lead assessor | Outstanding (vendor citing confidentiality; NDA review in progress) | Design | Pending | Vendor has not produced the report | Yes: escalated through VP Clinical Analytics; condition in POAM-016
EVID-052 | SA-22 | OS/database/runtime inventory with vendor support dates | Software lifecycle report | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-26 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/SA/EVID-052_eol-inventory.csv | No | Lead assessor | 3 unsupported components identified | Implementation | Sufficient |  | No
EVID-053 | SC-7; CM-6 | Security group rules for wf-sftp-01 and all groups with 0.0.0.0/0 ingress | EC2 DescribeSecurityGroups export | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-07-02 | Accepted | As of 2026-07-02 | evidence/CM/EVID-053_wf-sftp-01-security-group_2026-07-02.json | Yes | Lead assessor | RDP 3389 open to 0.0.0.0/0 | Implementation | Sufficient |  | No
EVID-054 | SC-8 | TLS policies and database SSL enforcement; external TLS scan | ALB/CloudFront policies + RDS parameter group + TLS scan | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/SC/EVID-054_tls.zip | No | Lead assessor | TLS 1.2+ only; force_ssl on | Implementation | Sufficient |  | No
EVID-055 | SC-12 | KMS key inventory, rotation, key policies | KMS ListKeys/GetKeyRotationStatus + policies | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/SC/EVID-055_kms.json | No | Lead assessor | 9 of 9 rotation enabled | Implementation | Sufficient |  | No
EVID-056 | SC-28 | Encryption status for all data stores; endpoint encryption compliance | Config rule results + MDM encryption report | Tomasz Wierzbicki | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/SC/EVID-056_encryption.zip | No | Lead assessor | 100% encrypted | Implementation | Sufficient |  | No
EVID-057 | SI-3 | EDR coverage reconciled to inventory | EDR sensor export + reconciliation | Owen Castillo | 2026-06-10 | 2026-06-19 | 2026-06-24 | Accepted | As of 2026-06-30 | GRC-Vault:/WCP-2026/SI/EVID-057_edr-coverage.csv | No | Lead assessor | 358 of 362 endpoints (4 in provisioning); 100% servers | Implementation | Sufficient |  | No
EVID-058 | SI-4; CA-7 | Detection inventory and MDR triage metrics; 10 sample alerts | Rule inventory (41) + MDR monthly reports + alert samples | Owen Castillo | 2026-06-10 | 2026-06-19 | 2026-06-26 | Accepted | 2026-01-01 to 2026-06-30 | GRC-Vault:/WCP-2026/SI/EVID-058_monitoring.zip | No | Lead assessor | 97% High alerts triaged within 30 min | Operating Effectiveness | Sufficient |  | No
EVID-059 | SR-2 | Approved C-SCRM plan | Draft outline (2 pages) | Beth Kowalski | 2026-06-10 | 2026-06-19 | 2026-06-19 | Insufficient | Current | GRC-Vault:/WCP-2026/SR/EVID-059_cscrm-outline.docx | No | Lead assessor | Outline only; not approved | Design | Insufficient | No C-SCRM plan | Yes: POAM-015
EVID-060 | RA-7; AC-5; PM-9 | Signed risk acceptance for SoD conflict | RACC-001 (signed CFO + CISO 2026-08-12) | Laura Brenneman | 2026-08-07 | 2026-08-14 | 2026-08-12 | Accepted | 2026-08-12 to 2027-03-31 | risk/risk-acceptance/RACC-001.md | Yes | Lead assessor | Signed at correct authority level with compensating control | Design | Sufficient |  | No
EVID-061 | AC-2; AC-2(3); PS-4; PS-5 | Revocation tickets for AR-EX-01/02/04/12/13/14 and all terminations 2026-07-01 to 2026-09-09 with de-provisioning timestamps | Jira IT tickets + Okta/portal deactivation records | Nadia Rahman | 2026-08-15 | 2026-09-10 | 2026-09-10 | Closed | 2026-07-01 to 2026-09-09 | evidence/AC/EVID-061_terminations-and-deactivations_2026-07-01_to_09-09.csv | Yes | Lead assessor | 7 of 7 terminations within 24h; all revocations verified in post-change exports | Operating Effectiveness | Sufficient |  | No
EVID-062 | AC-2(1); AC-2(3) | HR-to-Okta reconciliation job design and last 5 run outputs | Job output 2026-09-04 to 2026-09-10 + job runbook | Nadia Rahman | 2026-08-15 | 2026-09-10 | 2026-09-10 | Closed | 2026-09-04 to 2026-09-10 | evidence/AC/EVID-062_hr-okta-reconciliation-job_2026-09-10.csv | Yes | Lead assessor | 0 exceptions across 5 runs; covers Okta + AWS IAM + portal + contractor end dates | Operating Effectiveness | Sufficient |  | No
EVID-063 | IA-2(1); IA-2(2) | Okta policy export after remediation + group deletion record | Okta Policies API export 2026-09-04 | Nadia Rahman | 2026-08-15 | 2026-09-05 | 2026-09-04 | Closed | As of 2026-09-04 | evidence/IA/EVID-063_okta-authentication-policies_2026-09-04.json | Yes | Lead assessor | Exemption policy/group deleted; admin apps phishing-resistant; password-only sign-in denied (re-performed) | Implementation | Sufficient |  | No
EVID-064 | IA-2(1); IA-5; AC-2(3) | AWS IAM credential report after remediation | IAM credential report 2026-09-04 | Tomasz Wierzbicki | 2026-08-15 | 2026-09-05 | 2026-09-04 | Closed | As of 2026-09-04 | evidence/IA/EVID-064_aws-iam-credential-report_2026-09-04.csv | Yes | Lead assessor | Only break-glass IAM user remains (hardware MFA, no keys) | Implementation | Sufficient |  | No
EVID-065 | AC-2; IA-5 | Updated service-account register showing owners, rotation, federation changes | Service account register v2026-09 + change tickets | Nadia Rahman | 2026-08-15 | 2026-09-12 | 2026-09-11 | Closed | As of 2026-09-11 | GRC-Vault:/WCP-2026/IA/EVID-065_service-register-v2026-09.csv | No | Lead assessor | All 13 owned; stale credentials rotated or federated; shared EDR login disabled | Implementation | Sufficient |  | No
EVID-066 | PS-7 | Contractor end-date sync report and SOW amendment | Okta account-expiry report + SOW 2025-061 amendment 1 | Sofia Ricci | 2026-08-15 | 2026-09-10 | 2026-09-08 | Closed | As of 2026-09-08 | GRC-Vault:/WCP-2026/PS/EVID-066_contractor-expiry.csv | No | Lead assessor | All contractor accounts carry expiry = SOW end date; awu amendment executed 2026-07-22 | Implementation | Sufficient |  | No
EVID-067 | AU-11 | Retention configuration after change + oldest-record checks | S3 lifecycle + CloudWatch subscription + SIEM archive config + object age query | Owen Castillo | 2026-08-15 | 2026-09-15 | 2026-09-12 | Closed | As of 2026-09-12 | evidence/AU/EVID-067_log-retention-config_2026-09-12.json | Yes | Lead assessor | 400-day retention; objects from 2026-03-20 still present (182 days) | Implementation | Sufficient |  | No
EVID-068 | SC-7; CM-6 | Security group change record and Security Hub re-evaluation | CHG-2026-0521 + SG export + Security Hub PASSED status | Tomasz Wierzbicki | 2026-07-02 | 2026-07-10 | 2026-07-10 | Closed | As of 2026-07-10 | GRC-Vault:/WCP-2026/SC/EVID-068_sg-fix.zip | No | Lead assessor | 3389 rule removed; admin via SSM only; finding PASSED | Implementation | Sufficient |  | No
EVID-069 | CP-9(1) | Restore test record with timings and integrity checks | Restore test record 2026-08-27 (assessor observed) | Tomasz Wierzbicki | 2026-08-15 | 2026-09-01 | 2026-08-28 | Closed | 2026-08-27 | evidence/CP/EVID-069_restore-test-record_2026-08-27.md | Yes | Lead assessor | RTO 3h41m (target 4h); data loss 11 min (RPO 1h); integrity checks passed | Operating Effectiveness | Sufficient |  | No
EVID-070 | AT-2 | LMS completion report after enforcement | LMS report 2026-09-12 (344 of 347; 3 on leave) | Denise Yamamoto | 2026-08-15 | 2026-09-15 | 2026-09-14 | Under Review | As of 2026-09-12 | GRC-Vault:/WCP-2026/AT/EVID-070_lms-completion-2026-09-12.csv | No | Lead assessor | In review: verifying leave records for 3 exceptions against PeopleHub | Operating Effectiveness | Pending |  | Yes: complete review by 2026-09-25
EVID-071 | AC-6; AC-6(5) | Just-in-time elevation workflow design and a live elevation record | Design doc + screenshot of approval screen | Tomasz Wierzbicki | 2026-08-15 | 2026-09-12 | 2026-09-11 | Rework Required | As of 2026-09-10 | GRC-Vault:/WCP-2026/AC/EVID-071_jit-design.pdf | No | Lead assessor | Screenshot does not show a live elevation, approver, session expiry, or CloudTrail record | Design | Insufficient (rework) | Design-only evidence for an operating control | Yes: provide a live elevation record with CloudTrail AssumeRole event and auto-expiry
EVID-072 | AU-6 | Weekly review tickets W27–W37 after the backup-reviewer change | SEC ticket export W27–W37 | Owen Castillo | 2026-08-15 | 2026-09-15 | 2026-09-16 | Received | 2026-W27 to 2026-W37 | GRC-Vault:/WCP-2026/AU/EVID-072_reviews-W27-W37.csv | No | Lead assessor | Not yet reviewed (received after the due date) | Operating Effectiveness | Pending |  | Yes: review by 2026-09-25
EVID-073 | SA-9; SR-6 | Quarrystone contract amendment (redline) and interim US-only access confirmation | Amendment redline v3 + vendor letter confirming offshore access suspended 2026-07-24 | Beth Kowalski | 2026-08-15 | 2026-09-30 | 2026-09-15 | Under Review | As of 2026-09-15 | GRC-Vault:/WCP-2026/SR/EVID-073_quarrystone-amendment-v3.pdf | No | Lead assessor | Letter accepted as interim containment; amendment not yet executed | Design | Pending |  | Yes: executed amendment required before SHCA data flows
EVID-074 | AC-6(7) | Q3 2026 privileged access certification (new design) | Campaign in progress | Alicia Moreno | 2026-09-01 | 2026-09-30 |  | Requested | 2026-Q3 | GRC-Vault:/WCP-2026/AC/EVID-074_pending | No | Lead assessor | Not yet due | Operating Effectiveness | Pending |  | Yes: due 2026-09-30
EVID-075 | AC-6; AC-6(2); AC-6(5) | Identity Center assignment export after privilege reduction | Identity Center assignment export 2026-09-03 | Tomasz Wierzbicki | 2026-08-15 | 2026-09-05 | 2026-09-03 | Accepted | As of 2026-09-03 | GRC-Vault:/WCP-2026/AC/EVID-075_idc-assignments-2026-09-03.csv | No | Lead assessor | AdministratorAccess now on jkim-adm, lbaptiste-adm, twierzbicki (daily; pending AR-EX-10) + break-glass | Implementation | Sufficient |  | No
EVID-076 | AC-6(5) | GitHub org owners after reduction | GitHub org member export 2026-08-12 | Grace Lindqvist | 2026-08-10 | 2026-08-14 | 2026-08-12 | Accepted | As of 2026-08-12 | GRC-Vault:/WCP-2026/AC/EVID-076_github-owners-2026-08-12.csv | No | Lead assessor | 3 owners (shaddad, twierzbicki, jkim) | Implementation | Sufficient |  | No
EVID-077 | AC-6(5); AC-6(2) | Okta administrator role assignment report after change | Okta admin roles report 2026-07-21 | Nadia Rahman | 2026-07-20 | 2026-07-24 | 2026-07-21 | Accepted | As of 2026-07-21 | GRC-Vault:/WCP-2026/AC/EVID-077_okta-admin-roles-2026-07-21.csv | No | Lead assessor | Super Admin: nrahman-adm + break-glass only | Implementation | Sufficient |  | No
EVID-078 | IR-4; AC-2(3) | Investigation record for INC-2026-0117 (post-termination sign-in) | Incident record with timeline, log review, and breach risk assessment | Owen Castillo | 2026-07-06 | 2026-07-10 | 2026-07-09 | Accepted | 2026-07-06 to 2026-07-09 | evidence/IR/EVID-078_INC-2026-0117-investigation.md | Yes | Lead assessor | Contained same day; 4-factor assessment documented; no evidence of PHI access | Operating Effectiveness | Sufficient |  | No