## README
Plan of Action & Milestones (POA&M)
Wrenfield Health (fictional) · simulated NIST SP 800-53 Rev. 5 (Release 5.2.0) assessment · synthetic data
As-of (status) date | 2026-09-18 | <- input: all aging/overdue formulas reference this cell (use =TODAY() in a live workbook)
Scope | Every finding (FIND-nnn) has POAM-nnn, including the risk-accepted item: nothing silently drops off
SLA | From Open Date: Critical 30 / High 90 / Moderate 180 / Low 365 days (RSK-MTH-001 §9). SLA Date is a live formula
Original vs current target | Original target never changes. A changed current target needs a documented, approved reason; 'Slipped?' is a formula
Percent Complete | Formula: milestones Done / total milestones (Milestones sheet). No subjective percentages
Overdue? | Formula: status not Closed/Risk Accepted AND current target < as-of date
Closure rule | Status 'Closed' only after assessor validation with closure evidence (see Validation Method)

## POAM
POA&M ID | Related Finding | Related Control | Related Risk | Weakness | Root Cause | Severity | Corrective Action | Milestones | Owner | Resources Required | Open Date | SLA Date | Original Target Date | Current Target Date | Target Change Reason | Current Status | Percent Complete | Days Open | Overdue? | Slipped? | Target Within SLA? | Dependencies | Validation Method | Closure Evidence | Validated By | Closure Date | Residual Risk | Notes
POAM-001 | FIND-001 | AC-2(3); AC-2; AC-2(1); PS-4; PS-7 | RISK-002 | Terminated workforce retained active access (SSO, local AWS IAM, vendor portal) | Manual HR-email-to-IT ticketing with no automated trigger; local accounts not in offboarding checklist; contractor end dates not enforced | High | Disable identified accounts; implement daily HR-to-Okta/AWS/portal reconciliation with auto-ticketing; update SOP-IAM-02 with a local-account checklist and 24h SLA | M1 Disable 4 identified accounts (AR-EX-01..04); investigate post-termination sign-in (INC-2026-0117) (due 2026-07-10; Done) ¦ M2 Deploy daily HR-to-Okta/AWS IAM/portal reconciliation job with auto-ticketing (due 2026-08-21; Done) ¦ M3 Update SOP-IAM-02 (24h SLA, local-account checklist, vendor portals); train IT (due 2026-08-28; Done) ¦ M4 Assessor validation: re-perform termination test on all terminations since 2026-07-01 + 5 job runs (due 2026-09-11; Done) | Nadia Rahman (IAM Engineer) | IAM Engineer (about 60h); Okta Workflows (existing license); HR ops (4h) | 2026-08-07 |  | 2026-09-11 | 2026-09-11 |  | Closed | [5 empty] | Okta Workflows connector to PeopleHub | Re-performance: tools/assessment_tests.py termination-validation (7 of 7 within 24h, 0 job exceptions); inspection of IAM credential report (break-glass only) | EVID-061; EVID-062; EVID-064; EVID-078 | Lead assessor | 2026-09-10 | Moderate (RISK-002 residual L2 x I4 = 8) | Operating sample is small (7); full re-test scheduled for FY27.
POAM-002 | FIND-002 | IA-2(1); IA-2(2) | RISK-003 | MFA exemption group and AWS IAM user without MFA | Exceptions granted without workflow, expiry, or review; legacy IAM users bypass Okta policy | High | Delete exemption policy and group; enroll all members (hardware key accommodation); convert service users to integrations; require phishing-resistant MFA for admin apps; delete non-break-glass IAM users; add time-bound exception workflow | M1 Enroll 9 human members in MFA (accommodation for 1) (due 2026-08-28; Done) ¦ M2 Convert svc-vulnscan and svc-confroom to non-interactive integrations (due 2026-08-28; Done) ¦ M3 Delete Legacy Exemption Policy and group; phishing-resistant policy on admin apps (CHG-2026-0731) (due 2026-09-01; Done) ¦ M4 Assessor validation: policy export, group lookup, password-only sign-in attempt, IAM credential report (due 2026-09-05; Done) | Nadia Rahman (IAM Engineer) | IAM Engineer (about 30h); 12 FIDO2 keys (about $600) | 2026-08-07 |  | 2026-09-05 | 2026-09-05 |  | Closed | [5 empty] | Hardware key delivery for accessibility accommodation | Inspection of Okta policy export and IAM credential report; re-performance of password-only sign-in with a test account (denied) | EVID-063; EVID-064 | Lead assessor | 2026-09-05 | Moderate (RISK-003 residual L2 x I4 = 8)
POAM-003 | FIND-003 | AC-6(5); AC-6; AC-6(2) | RISK-001 | Excessive privileged access; administration from daily-use accounts | Privileged grants without expiry; no privileged-access review before 2026; separate-admin policy never rolled out | High | Remove excess grants; issue -adm accounts with phishing-resistant MFA; implement approval-gated JIT elevation for AWS admin; enforce GitHub owner cap | M1 Remove excess grants: AR-EX-05/06/07/08/09 (due 2026-08-21; Done) ¦ M2 Issue -adm accounts for remaining admins; remove admin from daily accounts (AR-EX-10) (due 2026-09-30; In Progress) ¦ M3 Implement JIT elevation (approval + 4h auto-expiry) for AWS AdministratorAccess (due 2026-10-23; In Progress) ¦ M4 Assessor validation: assignment export + live elevation record with CloudTrail evidence (due 2026-11-05; Not Started) | Tomasz Wierzbicki (Director, Platform Engineering) | SRE (about 80h); IAM Engineer (about 20h) | 2026-08-07 |  | 2026-11-05 | 2026-11-05 |  | In Progress | [5 empty] | IAM Identity Center permission-set redesign; EVID-071 returned as Rework Required (design-only evidence) | Inspection of Identity Center/GitHub/Okta admin exports; re-performance: request and observe a JIT elevation, confirm auto-expiry in CloudTrail | EVID-075; EVID-076; EVID-077; EVID-071 |  |  | Moderate target (RISK-001 residual L2 x I4 = 8); currently High | Evidence EVID-071 rejected: a screenshot of an approval screen shows the design, not that elevation operates.
POAM-004 | FIND-004 | AC-6(7); AC-2; PS-5 | RISK-004 | Access recertification incomplete in scope and ineffective in operation | Campaign scope limited to Okta app assignments; no usage data or risk flags for reviewers; no transfer trigger | Moderate | Redesign certification to cover all privileged and PHI entitlements on 9 systems with usage and baseline flags; require rationale for approving flagged items; transfer-triggered re-certification | M1 Revoke duplicate, transferred, and inactive access (AR-EX-12/13/14) (due 2026-07-17; Done) ¦ M2 Add transfer trigger to SOP-IAM-02 (re-baseline access within 5 business days) (due 2026-08-28; Done) ¦ M3 Run Q3 privileged certification on new design (EVID-074) (due 2026-09-30; In Progress) ¦ M4 Assessor validation: review Q3 campaign decisions for flagged items and rationale quality (due 2026-10-31; Not Started) | Alicia Moreno (CISO) | GRC Manager (about 40h); IAM Engineer (about 30h); review_engine.py reused as the flagging logic | 2026-08-07 |  | 2026-10-31 | 2026-10-31 |  | In Progress | [5 empty] | Q3 campaign completion by reviewers | Inspection of campaign export (population completeness vs entitlement exports; % flagged items with rationale; removals actioned) | EVID-061; EVID-074 |  |  | Moderate (RISK-004 residual L2 x I3 = 6)
POAM-005 | FIND-005 | IA-5; AC-2 | RISK-017 | Service/shared accounts without owners, stale credentials, shared vendor login | Service register lacked owner/rotation fields; vendor access set up for convenience | Moderate | Assign owners; rotate or federate stale credentials; named federated accounts for MDR analysts; add owner/rotation fields and quarterly attestation to the register | M1 Assign owners to all 13 non-human accounts; add fields to register (due 2026-08-21; Done) ¦ M2 Rotate svc-quarrystone-sftp key (AR-EX-18) (due 2026-08-28; Done) ¦ M3 Replace ironpeak-soc shared login with 6 named federated accounts (AR-EX-20) (due 2026-09-04; Done) ¦ M4 Migrate svc-reporting-etl to IAM role; delete IAM user (AR-EX-19) (due 2026-09-11; Done) ¦ M5 Assessor validation: register re-test (owner + credential age) and IAM credential report (due 2026-09-12; Done) | Nadia Rahman (IAM Engineer) | IAM Engineer (about 20h); SRE (about 16h) | 2026-08-07 |  | 2026-09-12 | 2026-09-12 |  | Closed | [5 empty] | Ironpeak MDR SSO onboarding | Re-performance of the review engine's service-account checks on the updated register; inspection of EDR console user list (no shared logins) | EVID-065; EVID-064 | Lead assessor | 2026-09-12 | Low (RISK-017 residual L1 x I4 = 4)
POAM-006 | FIND-006 | PS-7; AC-2 | RISK-002; RISK-004 | Contractor access not bound to engagement term and scope | Contract end dates not enforced in Okta; access requests not checked against SOW scope | Moderate | Okta account expiry = SOW end date for all contractors; SOW scope required on contractor access requests; monthly contractor roster to sponsors | M1 Execute SOW amendment for awu; revoke out-of-scope PHI access (AR-EX-15/16) (due 2026-07-24; Done) ¦ M2 Set Okta expiry for all contractor accounts; add SOW-scope field to access request form (due 2026-08-28; Done) ¦ M3 Assessor validation: expiry report vs SOW register (due 2026-09-10; Done) | Sofia Ricci (Engineering Manager) | IAM Engineer (about 8h); Vendor Mgmt (about 4h) | 2026-08-07 |  | 2026-09-10 | 2026-09-10 |  | Closed | [6 empty] | Inspection: Okta expiry dates reconciled to SOW register for all active contractors (29 of 29) | EVID-066 | Lead assessor | 2026-09-10 | Moderate (RISK-002 residual)
POAM-007 | FIND-007 | AC-5 | RISK-013 | SoD conflict (vendor master + payment approval) | Finance team reduced to 3 after AP departure | Moderate | Formal risk acceptance (RACC-001) with compensating monthly independent review; split roles when AP role is backfilled | M1 Sign RACC-001 (CFO as risk owner; CISO concurrence) (due 2026-08-14; Done) ¦ M2 Continue monthly compensating review (evidence each month to GRC) (due 2027-03-31; In Progress) ¦ M3 Split roles at AP backfill (requisition open) (due 2027-03-31; Not Started) | Laura Brenneman (Controller) | Controller (2h/month for compensating review) | 2026-08-07 |  | 2027-03-31 | 2027-03-31 |  | Risk Accepted | [5 empty] | AP Specialist hire | Monthly: GRC inspects signed vendor-master change report; at expiry: re-test role assignments | EVID-060; EVID-015 |  |  | Moderate, accepted (RISK-013 residual L2 x I3 = 6) | Accepted risks stay on the POA&M until expiry so they are re-decided, not forgotten.
POAM-008 | FIND-008 | AU-11 | RISK-005 | Audit log retention below 12-month requirement | 2022 cost-driven retention settings never revisited after contractual requirements emerged | Moderate | 400-day lifecycle with tiering (hot 90d searchable); archive application audit logs to log-archive; quarterly oldest-record check | M1 Change S3 lifecycle to 400-day expiry with Glacier IR after 90d (CHG-2026-0702) (due 2026-08-21; Done) ¦ M2 Subscribe app-audit CloudWatch logs to log-archive (Firehose) (due 2026-08-28; Done) ¦ M3 Assessor validation: config inspection + oldest-object query (due 2026-09-15; Done) | Owen Castillo (Security Engineer) | Security Engineer (about 16h); storage cost about $180/month | 2026-08-07 |  | 2026-09-15 | 2026-09-15 |  | Closed | [6 empty] | Inspection of lifecycle/subscription config; test: oldest CloudTrail object (2026-03-20, 182 days) still present after old 180-day rule would have expired it | EVID-067 | Lead assessor | 2026-09-15 | Moderate (RISK-005 residual after POAM-009) | Full 12-month retention can only be demonstrated over time; FY27 assessment re-tests.
POAM-009 | FIND-009 | AU-6 | RISK-005 | Weekly privileged-activity review missed 7 of 26 weeks; 2 incomplete | Single reviewer; no escalation; scope excluded local IAM users | Moderate | Backup reviewer (MDR under SOW change); auto-created weekly ticket with 5-day escalation; expand scope to all privileged principals; disposition required per flag | M1 Expand SIEM report scope to all privileged principals incl. IAM users (due 2026-08-21; Done) ¦ M2 Auto-create weekly review ticket with escalation to CISO at 5 business days (due 2026-08-28; Done) ¦ M3 Execute MDR SOW change for backup reviewer (due 2026-09-11; Delayed) ¦ M4 Assessor validation: W27–W37 reviews (EVID-072) (due 2026-09-15; Not Started) | Owen Castillo (Security Engineer) | MDR SOW change (about $1,500/month); Security Engineer (about 12h) | 2026-08-07 |  | 2026-09-15 | 2026-09-15 |  | In Progress | [5 empty] | Procurement approval of MDR SOW change (pending CFO signature) | Test: all weeks since change performed within 5 days with dispositions; inspect escalation config | EVID-072 |  |  | Moderate (RISK-005 residual L2 x I3 = 6) | Overdue since 2026-09-15; escalated to CISO 2026-09-16.
POAM-010 | FIND-010 | SI-2 | RISK-006 | 23% of Critical/High vulnerabilities exceeded SLA; exception process unused | End-of-life runtimes block patching; no exception discipline; SLA not visible in engineering planning; 7% untagged assets | High | Upgrade notify-worker runtime; file exceptions with reachability analysis where justified; SLA dashboard in sprint planning; tag-policy SCP | M1 Submit VM-003 §7 exception for 2 notify-worker criticals with reachability analysis (CISO decision) (due 2026-08-21; Done) ¦ M2 Upgrade notify-worker to supported Node.js LTS + current base image (due 2026-09-30; In Progress) ¦ M3 SLA-breach dashboard reviewed in weekly engineering leads meeting (due 2026-09-15; Done) ¦ M4 Tag-policy SCP denying untagged EC2/EKS launches (OBS-02) (due 2026-10-15; Not Started) ¦ M5 Assessor validation: re-run SLA test on Q3 population (due 2026-11-05; Not Started) | Grace Lindqvist (VP Engineering) | Engineering (about 3 sprint-weeks); Security Engineer (about 16h) | 2026-08-07 |  | 2026-11-05 | 2026-11-05 |  | In Progress | [5 empty] | FIND-011 (4 open breaches resolve only when legacy hosts are decommissioned) | Re-performance: tools/assessment_tests.py vulnsla on Q3 export (target: >= 95% within SLA, 0 open Critical past SLA without exception) |  |  |  | Moderate (RISK-006 residual L2 x I4 = 8) | CISO approved a 30-day exception for the 2 criticals (expires 2026-09-30) contingent on M2; consider SI-2(7) root cause analysis (OBS-04).
POAM-011 | FIND-011 | SA-22 | RISK-007 | Unsupported components (Windows 2012 R2 SFTP host, PostgreSQL 11, Node.js 16) in PHI path | Legacy integrations excluded from modernization; no lifecycle review for non-IaC assets | High | Avoid: replace wf-sftp-01 with managed transfer (IaC, PGP + SFTP, vendor/customer keys); migrate legacy-reports to supported Aurora replica; upgrade notify-worker (with POAM-010); maintain compensating controls until then | M1 Stand up managed transfer service (IaC) and test with Quarrystone (due 2026-08-28; Done) ¦ M2 Cut over Quarrystone + 4 customers; decommission wf-sftp-01 (due 2026-09-15; Delayed) ¦ M3 Migrate legacy-reports to Aurora read replica; decommission EC2 host (due 2026-10-30; In Progress) ¦ M4 Assessor validation: inventory shows 0 unsupported components; hosts terminated (due 2026-12-15; Not Started) | Tomasz Wierzbicki (Director, Platform Engineering) | SRE (about 120h); Customer Ops coordination with 4 customers + Quarrystone; managed transfer service about $400/month | 2026-08-07 |  | 2026-11-05 | 2026-12-15 | M2 slipped: 2 of 4 customers have not completed partner key exchange. SLA extension approved by CTO and CISO 2026-09-12 with compensating controls (EDR, allowlist, SSM-only admin, weekly scans); still ahead of SHCA go-live 2027-01-11. | Delayed | [5 empty] | Customer partner-side key exchange (2 of 4 pending); POAM-010 M2 for notify-worker | Inspection of EOL inventory and AWS Config (instances terminated); re-run vulnsla to confirm legacy-host findings closed |  |  |  | Low target (RISK-007 residual L1 x I4 = 4); currently High | Treatment is Avoid (decommission) rather than patching, which is not possible.
POAM-012 | FIND-012 | SC-7; CM-6 | RISK-012; RISK-007 | RDP open to 0.0.0.0/0 on wf-sftp-01; CSPM High finding untriaged 43 days | Console change path bypasses IaC/approval; Security Hub findings not routed to on-call | High | Remove rule; route Security Hub High findings to on-call with 7-day SLA; SCP guardrail blocking 0.0.0.0/0 on admin ports | M1 Remove 3389 ingress rule; confirm SSM-only admin (CHG-2026-0521); review Windows 4624 type-10 logons (due 2026-07-03; Done) ¦ M2 Route Security Hub High findings to SRE on-call queue (due 2026-07-08; Done) ¦ M3 Deploy SCP guardrail for admin ports from 0.0.0.0/0 (due 2026-07-10; Done) ¦ M4 Assessor validation: SG export, Security Hub PASSED, guardrail test (due 2026-07-10; Done) | Tomasz Wierzbicki (Director, Platform Engineering) | SRE (about 12h) | 2026-07-02 |  | 2026-07-10 | 2026-07-10 |  | Closed | [6 empty] | Inspection of SG and Security Hub status; re-performance: attempted to add 0.0.0.0/0:3389 rule in a sandbox OU account (denied by SCP) | EVID-068; EVID-053 | Lead assessor | 2026-07-10 | Moderate (RISK-012 residual L2 x I4 = 8) | Remediated during fieldwork. Still reported as a finding because the control failed during the period.
POAM-013 | FIND-013 | CP-9(1) | RISK-008 | Backup restoration never tested | Recoverability assumed from job success; no scheduled restore test | Moderate | Documented restore from DR vault into isolated account with timing and integrity checks; semi-annual schedule in BCP-003 | M1 Write restore runbook and integrity-check queries (due 2026-08-21; Done) ¦ M2 Perform restore test (assessor observes) (due 2026-08-28; Done) ¦ M3 Add semi-annual restore test to BCP-003 calendar; assessor validation (due 2026-09-01; Done) | Tomasz Wierzbicki (Director, Platform Engineering) | SRE (about 16h); isolated recovery account | 2026-08-07 |  | 2026-09-01 | 2026-09-01 |  | Closed | [6 empty] | Observation of restore test; inspection of timings vs RTO/RPO and integrity check output | EVID-069 | Lead assessor | 2026-09-01 | Moderate (RISK-008 residual L2 x I4 = 8, pending POAM-014)
POAM-014 | FIND-014 | IR-3; CP-4 | RISK-009; RISK-008 | IR and contingency plans not tested in 12+ months; SHCA 24h path unrehearsed | Exercises deferred twice without escalation | Moderate | Combined ransomware tabletop (IR + CP) with MDR, Legal/Privacy, Customer Ops, execs; update IRP-005 (SHCA 24h step, roster); track after-action items | M1 Update IRP-005: SHCA 24h notification step + current roster (OBS-03) (due 2026-09-15; Done) ¦ M2 Conduct ransomware tabletop (IR + CP) (due 2026-10-14; Not Started) ¦ M3 Publish after-action report; add corrective actions to POA&M (due 2026-10-30; Not Started) ¦ M4 Assessor validation (due 2026-11-15; Not Started) | Owen Castillo (Security Engineer) | Facilitator (MDR-provided, in contract); 3h of 12 participants | 2026-08-07 |  | 2026-11-15 | 2026-11-15 |  | In Progress | [5 empty] | Executive calendar availability | Inspection of exercise materials, attendance, after-action report; verify corrective actions are tracked |  |  |  | Moderate (RISK-009 residual L2 x I3 = 6)
POAM-015 | FIND-015 | SR-6; SA-9; SR-2 | RISK-011; RISK-010 | 5 of 14 Tier 1–2 vendors overdue; no fourth-party inventory; no C-SCRM plan | Under-resourced vendor program; spreadsheet tracking without reminders | Moderate | Clear overdue assessments (Tier 1 first); build fourth-party inventory; approve C-SCRM plan aligned to SP 800-161r1-upd1 / SP 800-18r2; renewal triggers | M1 Assess Tier 1 overdue vendors (Pulsewire, Ironpeak) (due 2026-11-30; In Progress) ¦ M2 Fourth-party inventory from updated questionnaires (all Tier 1) (due 2026-12-15; Not Started) ¦ M3 Approve C-SCRM plan (due 2027-01-15; Not Started) ¦ M4 Assess remaining Tier 2 overdue vendors; assessor validation (due 2027-02-03; Not Started) | Beth Kowalski (Vendor Management Lead) | Vendor Mgmt (about 0.5 FTE for 4 months); GRC Manager support | 2026-08-07 |  | 2027-02-03 | 2027-02-03 |  | In Progress | [5 empty] | Vendor responsiveness | Inspection of vendor register (100% Tier 1–2 within frequency) and approved C-SCRM plan |  |  |  | Moderate (RISK-011 residual L2 x I4 = 8)
POAM-016 | FIND-016 | SA-9; SR-6 | RISK-010 | Quarrystone: offshore PHI access, 30-day breach notice, excessive data fields, stale pentest | 2023 contract on vendor paper before TPRM-007; self-attestation relied on; extract not designed for minimum necessary | High | Contract amendment (US-only + technical enforcement, 24h notice, subcontractor approval, data return/destruction 30 days with certificate, log cooperation); minimize extract to scoring-required fields with tokenized IDs; obtain current pentest + retest; SHCA data blocked until conditions met | M1 Interim: vendor suspends offshore access to Wrenfield data (letter) (due 2026-07-24; Done) ¦ M2 Execute contract amendment (redline v3 in negotiation) (due 2026-09-30; In Progress) ¦ M3 Deploy minimized, tokenized extract (drop address, phone, email, free text) (due 2026-10-16; In Progress) ¦ M4 Receive current pentest report + retest letter (EVID-051) (due 2026-10-30; Not Started) ¦ M5 Assessor validation + vendor risk re-score (due 2026-11-05; Not Started) | Dr. Miriam Castell (VP Clinical Analytics) | General Counsel (about 20h); Data Engineering (about 60h for extract redesign); Vendor Mgmt | 2026-08-07 |  | 2026-11-05 | 2026-11-05 |  | In Progress | [5 empty] | Vendor negotiation; Quarrystone model retraining on minimized fields | Inspection of executed amendment; test: sample extract file schema vs approved minimum field list; inspection of pentest/retest; vendor attestation of US-only access with access-log sample | EVID-073; EVID-051 |  |  | Moderate target (RISK-010 residual L2 x I4 = 8); currently High | VR-001 (Critical) escalated to CEO 2026-07-17 per risk appetite; CEO approved conditional continuation 2026-07-22.
POAM-017 | FIND-017 | PL-2 | RISK-016 | SSP outdated; overstates implementation of 27 of 61 controls | SSP maintained as SOC 2 narrative; no update trigger on architecture change | Low | Rewrite SSP control-by-control from the validated matrix (SP 800-18 Rev. 2 structure); add architecture-change trigger in CMP-006 | M1 SSP outline on SP 800-18r2 structure; boundary + data flows updated (due 2026-09-30; In Progress) ¦ M2 Control implementation statements (61 controls) reviewed by owners (due 2026-11-30; Not Started) ¦ M3 Approval by CTO (system owner); assessor validation (due 2026-12-15; Not Started) | Priya Raman (Security Compliance Manager) | GRC Manager (about 80h); control owner reviews | 2026-08-07 |  | 2026-12-15 | 2026-12-15 |  | In Progress | [5 empty] | Control owners' review time | Inspection: SSP statements traced to matrix determinations (sample 15 controls) |  |  |  | Low (RISK-016 residual)
POAM-018 | FIND-018 | CM-3 | RISK-014 | Emergency and console changes bypass approval (3 of 25 sampled) | Console/emergency paths rely on memory; no retro-approval tracking | Moderate | Auto-open retro-approval task on every emergency change with 2-day escalation; CloudTrail/EventBridge alerts on console changes to security groups and IAM; approval gate before deploy job | M1 Retro-approval task automation for emergency changes (due 2026-08-28; Done) ¦ M2 EventBridge alerts on console SG/IAM changes to on-call (due 2026-09-04; Not Started) ¦ M3 Assessor validation: sample of emergency changes since M1 + alert test (due 2026-09-11; Not Started) | Tomasz Wierzbicki (Director, Platform Engineering) | SRE (about 24h) | 2026-08-07 |  | 2026-09-11 | 2026-09-11 |  | In Progress | [5 empty] | SRE backlog capacity (competing with POAM-011) | Test: all emergency changes since 2026-08-28 retro-approved within 2 business days; trigger a test SG change and confirm alert |  |  |  | Moderate (RISK-014 residual L2 x I3 = 6) | Overdue since 2026-09-11; needs CTO prioritization decision against POAM-011 (same SRE team).
POAM-019 | FIND-019 | AT-2 | RISK-015 | Security awareness training completion 91%; suspension not enforced | Reminders to users only; no manager escalation or enforcement | Low | Okta group rule enforcing suspension at 30 days overdue; manager escalation at 14 days; monthly completion reporting | M1 Manager escalation at 14 days; enforcement group rule live (due 2026-08-21; Done) ¦ M2 Reach >= 99% (documented leave exceptions) (due 2026-09-15; Done) ¦ M3 Assessor validation of EVID-070 (leave records for 3 exceptions) (due 2026-09-30; In Progress) | Denise Yamamoto (Director of People) | People Ops (about 8h); IAM Engineer (about 4h) | 2026-08-07 |  | 2026-09-30 | 2026-09-30 |  | Completed – Pending Validation | [6 empty] | Inspection: LMS roster reconciled to Okta active population; leave exceptions verified in PeopleHub | EVID-070 |  |  | Moderate, accepted (RISK-015 residual L3 x I3 = 9)

## Milestones
POA&M ID | Milestone | Description | Due Date | Status | Completed Date | Late?
POAM-001 | M1 | Disable 4 identified accounts (AR-EX-01..04); investigate post-termination sign-in (INC-2026-0117) | 2026-07-10 | Done | 2026-07-09
POAM-001 | M2 | Deploy daily HR-to-Okta/AWS IAM/portal reconciliation job with auto-ticketing | 2026-08-21 | Done | 2026-08-03
POAM-001 | M3 | Update SOP-IAM-02 (24h SLA, local-account checklist, vendor portals); train IT | 2026-08-28 | Done | 2026-08-26
POAM-001 | M4 | Assessor validation: re-perform termination test on all terminations since 2026-07-01 + 5 job runs | 2026-09-11 | Done | 2026-09-10
POAM-002 | M1 | Enroll 9 human members in MFA (accommodation for 1) | 2026-08-28 | Done | 2026-08-27
POAM-002 | M2 | Convert svc-vulnscan and svc-confroom to non-interactive integrations | 2026-08-28 | Done | 2026-08-27
POAM-002 | M3 | Delete Legacy Exemption Policy and group; phishing-resistant policy on admin apps (CHG-2026-0731) | 2026-09-01 | Done | 2026-08-28
POAM-002 | M4 | Assessor validation: policy export, group lookup, password-only sign-in attempt, IAM credential report | 2026-09-05 | Done | 2026-09-05
POAM-003 | M1 | Remove excess grants: AR-EX-05/06/07/08/09 | 2026-08-21 | Done | 2026-08-20
POAM-003 | M2 | Issue -adm accounts for remaining admins; remove admin from daily accounts (AR-EX-10) | 2026-09-30 | In Progress
POAM-003 | M3 | Implement JIT elevation (approval + 4h auto-expiry) for AWS AdministratorAccess | 2026-10-23 | In Progress
POAM-003 | M4 | Assessor validation: assignment export + live elevation record with CloudTrail evidence | 2026-11-05 | Not Started
POAM-004 | M1 | Revoke duplicate, transferred, and inactive access (AR-EX-12/13/14) | 2026-07-17 | Done | 2026-07-14
POAM-004 | M2 | Add transfer trigger to SOP-IAM-02 (re-baseline access within 5 business days) | 2026-08-28 | Done | 2026-08-25
POAM-004 | M3 | Run Q3 privileged certification on new design (EVID-074) | 2026-09-30 | In Progress
POAM-004 | M4 | Assessor validation: review Q3 campaign decisions for flagged items and rationale quality | 2026-10-31 | Not Started
POAM-005 | M1 | Assign owners to all 13 non-human accounts; add fields to register | 2026-08-21 | Done | 2026-08-18
POAM-005 | M2 | Rotate svc-quarrystone-sftp key (AR-EX-18) | 2026-08-28 | Done | 2026-08-25
POAM-005 | M3 | Replace ironpeak-soc shared login with 6 named federated accounts (AR-EX-20) | 2026-09-04 | Done | 2026-08-31
POAM-005 | M4 | Migrate svc-reporting-etl to IAM role; delete IAM user (AR-EX-19) | 2026-09-11 | Done | 2026-09-03
POAM-005 | M5 | Assessor validation: register re-test (owner + credential age) and IAM credential report | 2026-09-12 | Done | 2026-09-12
POAM-006 | M1 | Execute SOW amendment for awu; revoke out-of-scope PHI access (AR-EX-15/16) | 2026-07-24 | Done | 2026-07-22
POAM-006 | M2 | Set Okta expiry for all contractor accounts; add SOW-scope field to access request form | 2026-08-28 | Done | 2026-08-24
POAM-006 | M3 | Assessor validation: expiry report vs SOW register | 2026-09-10 | Done | 2026-09-08
POAM-007 | M1 | Sign RACC-001 (CFO as risk owner; CISO concurrence) | 2026-08-14 | Done | 2026-08-12
POAM-007 | M2 | Continue monthly compensating review (evidence each month to GRC) | 2027-03-31 | In Progress
POAM-007 | M3 | Split roles at AP backfill (requisition open) | 2027-03-31 | Not Started
POAM-008 | M1 | Change S3 lifecycle to 400-day expiry with Glacier IR after 90d (CHG-2026-0702) | 2026-08-21 | Done | 2026-08-19
POAM-008 | M2 | Subscribe app-audit CloudWatch logs to log-archive (Firehose) | 2026-08-28 | Done | 2026-08-27
POAM-008 | M3 | Assessor validation: config inspection + oldest-object query | 2026-09-15 | Done | 2026-09-12
POAM-009 | M1 | Expand SIEM report scope to all privileged principals incl. IAM users | 2026-08-21 | Done | 2026-08-14
POAM-009 | M2 | Auto-create weekly review ticket with escalation to CISO at 5 business days | 2026-08-28 | Done | 2026-08-28
POAM-009 | M3 | Execute MDR SOW change for backup reviewer | 2026-09-11 | Delayed
POAM-009 | M4 | Assessor validation: W27–W37 reviews (EVID-072) | 2026-09-15 | Not Started
POAM-010 | M1 | Submit VM-003 §7 exception for 2 notify-worker criticals with reachability analysis (CISO decision) | 2026-08-21 | Done | 2026-08-20
POAM-010 | M2 | Upgrade notify-worker to supported Node.js LTS + current base image | 2026-09-30 | In Progress
POAM-010 | M3 | SLA-breach dashboard reviewed in weekly engineering leads meeting | 2026-09-15 | Done | 2026-09-09
POAM-010 | M4 | Tag-policy SCP denying untagged EC2/EKS launches (OBS-02) | 2026-10-15 | Not Started
POAM-010 | M5 | Assessor validation: re-run SLA test on Q3 population | 2026-11-05 | Not Started
POAM-011 | M1 | Stand up managed transfer service (IaC) and test with Quarrystone | 2026-08-28 | Done | 2026-08-26
POAM-011 | M2 | Cut over Quarrystone + 4 customers; decommission wf-sftp-01 | 2026-09-15 | Delayed
POAM-011 | M3 | Migrate legacy-reports to Aurora read replica; decommission EC2 host | 2026-10-30 | In Progress
POAM-011 | M4 | Assessor validation: inventory shows 0 unsupported components; hosts terminated | 2026-12-15 | Not Started
POAM-012 | M1 | Remove 3389 ingress rule; confirm SSM-only admin (CHG-2026-0521); review Windows 4624 type-10 logons | 2026-07-03 | Done | 2026-07-03
POAM-012 | M2 | Route Security Hub High findings to SRE on-call queue | 2026-07-08 | Done | 2026-07-07
POAM-012 | M3 | Deploy SCP guardrail for admin ports from 0.0.0.0/0 | 2026-07-10 | Done | 2026-07-09
POAM-012 | M4 | Assessor validation: SG export, Security Hub PASSED, guardrail test | 2026-07-10 | Done | 2026-07-10
POAM-013 | M1 | Write restore runbook and integrity-check queries | 2026-08-21 | Done | 2026-08-19
POAM-013 | M2 | Perform restore test (assessor observes) | 2026-08-28 | Done | 2026-08-27
POAM-013 | M3 | Add semi-annual restore test to BCP-003 calendar; assessor validation | 2026-09-01 | Done | 2026-09-01
POAM-014 | M1 | Update IRP-005: SHCA 24h notification step + current roster (OBS-03) | 2026-09-15 | Done | 2026-09-11
POAM-014 | M2 | Conduct ransomware tabletop (IR + CP) | 2026-10-14 | Not Started
POAM-014 | M3 | Publish after-action report; add corrective actions to POA&M | 2026-10-30 | Not Started
POAM-014 | M4 | Assessor validation | 2026-11-15 | Not Started
POAM-015 | M1 | Assess Tier 1 overdue vendors (Pulsewire, Ironpeak) | 2026-11-30 | In Progress
POAM-015 | M2 | Fourth-party inventory from updated questionnaires (all Tier 1) | 2026-12-15 | Not Started
POAM-015 | M3 | Approve C-SCRM plan | 2027-01-15 | Not Started
POAM-015 | M4 | Assess remaining Tier 2 overdue vendors; assessor validation | 2027-02-03 | Not Started
POAM-016 | M1 | Interim: vendor suspends offshore access to Wrenfield data (letter) | 2026-07-24 | Done | 2026-07-24
POAM-016 | M2 | Execute contract amendment (redline v3 in negotiation) | 2026-09-30 | In Progress
POAM-016 | M3 | Deploy minimized, tokenized extract (drop address, phone, email, free text) | 2026-10-16 | In Progress
POAM-016 | M4 | Receive current pentest report + retest letter (EVID-051) | 2026-10-30 | Not Started
POAM-016 | M5 | Assessor validation + vendor risk re-score | 2026-11-05 | Not Started
POAM-017 | M1 | SSP outline on SP 800-18r2 structure; boundary + data flows updated | 2026-09-30 | In Progress
POAM-017 | M2 | Control implementation statements (61 controls) reviewed by owners | 2026-11-30 | Not Started
POAM-017 | M3 | Approval by CTO (system owner); assessor validation | 2026-12-15 | Not Started
POAM-018 | M1 | Retro-approval task automation for emergency changes | 2026-08-28 | Done | 2026-08-28
POAM-018 | M2 | EventBridge alerts on console SG/IAM changes to on-call | 2026-09-04 | Not Started
POAM-018 | M3 | Assessor validation: sample of emergency changes since M1 + alert test | 2026-09-11 | Not Started
POAM-019 | M1 | Manager escalation at 14 days; enforcement group rule live | 2026-08-21 | Done | 2026-08-20
POAM-019 | M2 | Reach >= 99% (documented leave exceptions) | 2026-09-15 | Done | 2026-09-12
POAM-019 | M3 | Assessor validation of EVID-070 (leave records for 3 exceptions) | 2026-09-30 | In Progress