## README
Enterprise Cybersecurity Risk Register
Wrenfield Health (fictional) · simulated NIST SP 800-53 Rev. 5 (Release 5.2.0) assessment · synthetic data
As-of (status) date | 2026-09-18 | <- input: all aging/overdue formulas reference this cell (use =TODAY() in a live workbook)
Method | RSK-MTH-001 (risk/risk-methodology.md): 1-5 likelihood x 1-5 impact, adapted from NIST SP 800-30 Rev. 1
Formulas | Score = Likelihood x Impact. Rating = IF(score>=20,Critical, >=10 High, >=5 Moderate, else Low). Edit L/I and scores recalculate
Three states | Inherent (no controls) -> Current (controls as tested; failed controls earn no credit) -> Residual (target after treatment)
Rationale | Every L and I value has a written rationale (right-most columns). A score without rationale is not accepted
Limitation | Ordinal scales: multiplication is a prioritization convention, not a measurement. Ties broken by Impact, then Likelihood

## Risks
Risk ID | Risk Title | Risk Description | Asset / Process | Threat | Vulnerability | Existing Controls | Inherent Likelihood | Inherent Impact | Inherent Score | Inherent Risk | Current Likelihood | Current Impact | Current Score | Current Risk | Treatment Strategy | Planned Mitigation | Risk Owner | Target Date | Residual Likelihood | Residual Impact | Residual Score | Residual Risk | Status | Related NIST Controls | Related Findings | Related POA&M | Review Date | Rationale: Inherent | Rationale: Current | Rationale: Residual
RISK-001 | Privileged cloud or identity admin account misused or compromised | An attacker phishes or steals the session of a user holding production AdministratorAccess, Okta Super Admin, or GitHub owner, then exfiltrates PHI or destroys infrastructure. | AWS wcp-prod admin plane, Okta tenant, GitHub org | External actor (phishing, session-token theft) or malicious/negligent insider | Excess admin grants; admin performed from daily-use accounts; no JIT elevation | Okta SSO+MFA for most users; CloudTrail and GuardDuty; MDR 24x7; Vault Lock on backups | 4 | 5 |  |  | 3 | 5 |  |  | Mitigate | Remove excess grants; -adm accounts; JIT elevation; GitHub owner cap (POAM-003) | Samir Haddad (CTO) | 2026-11-05 | 2 | 4 |  |  | Treatment in progress | AC-6; AC-6(2); AC-6(5); IA-2(1) | FIND-003 | POAM-003 | 2026-09-18 | L4: identity-based intrusion is the dominant cloud attack path. I5: admin reaches all PHI (>50k records) and can cause an outage over 24h. | L3: MFA and monitoring raise attacker effort, but 6 unjustified or daily-account admin assignments existed. I5 unchanged: any admin can still reach everything. | L2: -adm accounts with phishing-resistant MFA plus approval-gated JIT elevation. I4: time-boxed sessions and Vault Lock limit destructive impact and dwell time, but exfiltration during a session is still possible.
RISK-002 | Unauthorized access by former employees or contractors | A departed worker's still-active account is used, by them or by an attacker, to access PHI or financial systems. | All in-scope systems, including Ledgerline and the vendor portal | Former workforce member (disgruntled or careless), or an attacker using an orphaned account | Manual de-provisioning; local accounts outside SSO; contractor end dates not enforced | Okta deactivation by IT ticket; asset recovery at exit | 4 | 4 |  |  | 4 | 4 |  |  | Mitigate | HR-to-Okta reconciliation with auto-ticketing; contractor expiry; local-account cleanup (POAM-001, POAM-006) | Alicia Moreno (CISO) | 2026-09-10 | 2 | 4 |  |  | Treated (residual achieved; monitoring) | AC-2; AC-2(1); AC-2(3); PS-4; PS-7 | FIND-001; FIND-006 | POAM-001; POAM-006 | 2026-09-18 | L4: turnover of about 38/year plus contractors, and orphaned accounts are a well-known misuse path. I4: AWS admin or PHI DB access affects 500–50,000+ records; limited by role mix. | L4 unchanged: the control failed testing (2 of 19 not disabled, 1 post-termination sign-in, local admin account active 95 days) and earns no credit. I4. | L2: daily reconciliation job, contractor account expiry, and a local-account inventory, validated 7 of 7. I4 unchanged: a missed account could still reach sensitive data.
RISK-003 | Account takeover through MFA gaps | An attacker obtains the password of an MFA-exempt account and signs in directly, inheriting that user's access, including identity administration. | Okta and all federated systems | Credential phishing, password spraying, reuse of breached credentials | MFA exemption group (9 humans incl. an Okta Super Admin); IAM user without MFA | Global MFA policy for 97% of users; replay-resistant authenticators; Okta ThreatInsight | 4 | 5 |  |  | 3 | 5 |  |  | Mitigate | Delete the exemption policy; enroll all users; phishing-resistant admin MFA; exception workflow (POAM-002) | Alicia Moreno (CISO) | 2026-09-05 | 2 | 4 |  |  | Treated (residual achieved; monitoring) | IA-2(1); IA-2(2); IA-2(8) | FIND-002 | POAM-002 | 2026-09-18 | L4: phishing is the leading initial-access vector. I5: federation reaches AWS prod and PHI. | L3: MFA covers 97%, a partial control. I5: an exempt Okta Super Admin could reach everything. | L2: no exemptions; phishing-resistant MFA for admins; token theft still possible. I4: least-privilege work narrows what one account reaches.
RISK-004 | Access creep from ineffective recertification | Users accumulate access beyond need over time, increasing the blast radius of any compromise or misuse. | Privileged and PHI entitlements across 9 systems | Insider misuse; attacker leveraging over-privileged accounts | Rubber-stamp reviews; privileged systems out of review scope; no re-baseline on transfer | Quarterly Okta app certification (limited scope) | 4 | 3 |  |  | 4 | 3 |  |  | Mitigate | Redesign certifications; transfer-triggered review (POAM-004) | Alicia Moreno (CISO) | 2026-10-31 | 2 | 3 |  |  | Treatment in progress | AC-6(7); AC-2; PS-5 | FIND-004; FIND-006 | POAM-004 | 2026-09-18 | L4: fast growth, transfers, and contractors make creep near-certain without review. I3: creep usually adds read access; worst credible case is fewer than 500 records. | L4: the review operated but was ineffective (100% approval, key systems excluded), so no credit. I3. | L2: full-scope campaigns with usage data and flagged items needing rationale. I3.
RISK-005 | Inability to detect or investigate PHI access | Misuse goes unnoticed, or a breach found months later cannot be scoped, forcing presumptive notification of large patient populations. | Audit logs (CloudTrail, application PHI-access audit, SIEM) | Undetected insider or attacker activity; late-discovered breach | 90–180-day retention; inconsistent privileged-activity review | Comprehensive event logging (AU-2); immutable log archive (AU-9); MDR alerting (SI-4) | 3 | 4 |  |  | 3 | 4 |  |  | Mitigate | Extend retention (POAM-008, done); backup reviewer and escalation (POAM-009) | Alicia Moreno (CISO) | 2026-10-31 | 2 | 3 |  |  | Treatment in progress | AU-6; AU-11; AU-2; AU-9 | FIND-008; FIND-009 | POAM-008; POAM-009 | 2026-09-18 | L3: breaches are often discovered after 90+ days. I4: inability to scope means broad notification plus contract breach. | L3: logging is strong, but retention is short and 35% of weekly reviews were missed or incomplete. I4. | L2: 400-day retention plus a backup reviewer. I3: records now exist to scope and limit notification.
RISK-006 | Exploitation of unremediated vulnerabilities | An attacker exploits a known, unpatched flaw in a production service or host to gain a foothold. | Internet-facing services and container workloads | Opportunistic exploitation of known CVEs; ransomware affiliates | 23% SLA misses; end-of-life runtimes; exception process unused | WAF; weekly authenticated scanning; container image scanning; EDR; MDR | 4 | 5 |  |  | 3 | 4 |  |  | Mitigate | Upgrade EOL runtimes; exception process; SLA reporting; tag enforcement (POAM-010) | Grace Lindqvist (VP Engineering) | 2026-11-05 | 2 | 4 |  |  | Treatment in progress | RA-5; SI-2; CM-8 | FIND-010 | POAM-010 | 2026-09-18 | L4: exploitation of known vulnerabilities is a top initial-access vector. I5: PHI platform compromise. | L3: scanning, WAF, and EDR are effective layers, but 6 items are open past SLA. I4: segmentation (private subnets) limits the blast radius from most workloads. | L2: SLA adherence with governed exceptions. I4: same architecture.
RISK-007 | Compromise of unsupported legacy components in the PHI path | An attacker exploits an unpatchable flaw on the legacy SFTP host, which holds the nightly full-PHI extract, and pivots or exfiltrates. | wf-sftp-01 (Windows 2012 R2), legacy-reports (PostgreSQL 11), notify-worker (Node 16) | Exploitation of unpatchable flaws; ransomware | No vendor patches; host previously exposed via internet-facing RDP | EDR; SFTP source allowlist; weekly scanning; SSM-only admin (after FIND-012 fix) | 4 | 4 |  |  | 3 | 4 |  |  | Avoid | Decommission wf-sftp-01 and legacy-reports; upgrade notify-worker (POAM-011) | Samir Haddad (CTO) | 2026-12-15 | 1 | 4 |  |  | Treatment in progress (delayed) | SA-22; SC-7; CM-6; SI-2 | FIND-011; FIND-012 | POAM-011; POAM-012 | 2026-09-18 | L4: unsupported, internet-reachable Windows host. I4: a full-PHI extract sits there transiently (worst credible case is one night's file, bounded). | L3: RDP closed, allowlist and EDR in place, but no patches. I4. | L1: components decommissioned (Avoid). I4 kept, because the managed-transfer replacement still moves the same data.
RISK-008 | Failed or slow recovery from ransomware or data corruption | A destructive event forces recovery, and recovery takes longer than RTO or loses data because the process was never exercised. | wcp-core-db and WCP services | Ransomware; destructive insider; data corruption | Restore never tested (at fieldwork); contingency plan untested | PITR (35 days); cross-region, cross-account backups with Vault Lock; BC/DR plan | 3 | 5 |  |  | 2 | 5 |  |  | Mitigate | Semi-annual restore tests (POAM-013, done); CP exercise (POAM-014) | Samir Haddad (CTO) | 2026-11-15 | 2 | 4 |  |  | Treatment in progress | CP-2; CP-4; CP-9; CP-9(1) | FIND-013; FIND-014 | POAM-013; POAM-014 | 2026-09-18 | L3: healthcare ransomware frequency. I5: outage over 24h for clinical workflows. | L2: strong, immutable backups reduce the chance of an unrecoverable event. I5: recovery time was unproven. | L2. I4: restore proven at 3h41m (within the 4h RTO); a full contingency exercise is pending (POAM-014).
RISK-009 | Delayed or ineffective response to a major incident | During a major incident, unclear roles or notification steps delay containment or cause a missed contractual or regulatory notification deadline. | Incident response capability and notification obligations | Major incident (ransomware, large PHI breach) stressing untested processes | No IR exercise in 21 months; SHCA 24h path never rehearsed | IRP-005 (current); 24x7 MDR; incidents in H1 handled well (IR-4 satisfied) | 3 | 4 |  |  | 3 | 4 |  |  | Mitigate | Ransomware tabletop and plan update (POAM-014) | Alicia Moreno (CISO) | 2026-11-15 | 2 | 3 |  |  | Treatment in progress | IR-3; IR-4; IR-6; IR-8 | FIND-014 | POAM-014 | 2026-09-18 | L3: at least one significant incident per year is plausible. I4: missed notification means a contract breach and regulatory scrutiny. | L3: good day-to-day handling, but major-incident paths are untested. I4. | L2: rehearsed plan with the SHCA step. I3: faster, coordinated response limits impact.
RISK-010 | PHI exposure through the analytics vendor (Quarrystone) | A breach at Quarrystone or its offshore subcontractor exposes Wrenfield PHI, and notice arrives too late for Wrenfield to meet 24h or 5-day obligations. | Nightly full-PHI extract (about 410k patients) processed by Quarrystone and its subcontractors | Vendor or subcontractor breach; unauthorized offshore access; delayed breach notice | Offshore subcontractor access; 30-day notice term; excess data fields; stale pentest | BAA; SOC 2 Type II (unqualified); encryption in transit and at rest; interim suspension of offshore access (2026-07-24) | 4 | 5 |  |  | 3 | 5 |  |  | Mitigate | Contract amendment; data minimization; pentest and retest; monitoring plan (POAM-016). Transfer (partial) through cyber insurance and vendor indemnity. | Dr. Miriam Castell (VP Clinical Analytics) | 2026-11-05 | 2 | 4 |  |  | Treatment in progress | SA-9; SR-6; CA-3 | FIND-016; FIND-015 | POAM-016; POAM-015 | 2026-09-18 | L4: third-party breaches are frequent in healthcare, and an undisclosed offshore party was present. I5: >50k records plus SHCA contract loss. | L3: vendor controls are generally mature (SOC 2, encryption) and offshore access is suspended, but the contract terms are unchanged. I5. | L2: contractual US-only with technical enforcement, 24h notice, and current pentest. I4: minimized extract (no contact details or free text) reduces the records and sensitivity exposed.
RISK-011 | Software or vendor supply-chain compromise | A compromised dependency or vendor integration introduces malicious code or access into WCP. | CI/CD pipeline, open-source dependencies, vendor integrations | Malicious dependency or compromised vendor update or integration | No C-SCRM plan; no fourth-party inventory; 5 vendors overdue for review | Dependency scanning; branch protection and required review; OIDC deploy (no static keys); pinned base images | 3 | 5 |  |  | 3 | 4 |  |  | Mitigate | C-SCRM plan; clear the vendor backlog; fourth-party inventory (POAM-015) | Beth Kowalski (Vendor Management Lead) | 2027-02-03 | 2 | 4 |  |  | Treatment in progress | SR-2; SR-6; SA-9 | FIND-015 | POAM-015 | 2026-09-18 | L3: supply-chain attacks are increasing. I5: code execution in the PHI platform. | L3: good pipeline hygiene, but no program-level supply chain risk management. I4: OIDC and least-privilege deploy roles limit what a compromised pipeline can reach. | L2: C-SCRM plan, current vendor reviews, fourth-party visibility. I4.
RISK-012 | Cloud misconfiguration exposing PHI or admin services | A manual misconfiguration (an open port, a public resource) exposes PHI or an admin interface to the internet. | AWS wcp-prod network and storage configuration | Opportunistic internet scanning; misconfiguration exploited by attackers | Console changes bypass IaC; CSPM findings not routed to on-call | Org-wide S3 Block Public Access (SCP); encryption by default; Security Hub CIS checks; IaC for most resources | 4 | 5 |  |  | 2 | 5 |  |  | Mitigate | Route CSPM to on-call; admin-port guardrail; emergency change auto-revert (POAM-012, POAM-018) | Tomasz Wierzbicki (Director, Platform Engineering) | 2026-09-11 | 2 | 4 |  |  | Treatment in progress | CM-2; CM-6; SC-7; SC-28 | FIND-012 | POAM-012 | 2026-09-18 | L4: misconfiguration is a leading cloud breach cause. I5: public PHI exposure. | L2: strong preventive guardrails for data stores (block public access, encryption). The observed exposure was an admin port, not data. I5: remains the worst credible case. | L2: CSPM routed to on-call plus SCP guardrails on admin ports. I4: guardrails prevent the most severe (data-store) exposures.
RISK-013 | Fraudulent vendor payment through an SoD conflict | A user alters vendor bank details and approves payments to an attacker-controlled account. | Ledgerline vendor master and payments | Insider fraud or coerced insider (business email compromise) | One user holds vendor-master maintenance and payment approval (≤ $25k) | Compensating: monthly vendor-master change report reviewed by the Controller; callback verification of bank-detail changes; payments over $25k need CFO approval | 3 | 3 |  |  | 2 | 3 |  |  | Accept | RACC-001 risk acceptance with compensating control; split roles at AP backfill (POAM-007) | Raymond Okafor (CFO) | 2027-03-31 | 2 | 3 |  |  | Accepted (RACC-001, expires 2027-03-31) | AC-5 | FIND-007 | POAM-007 | 2026-09-18 | L3: BEC-driven bank-change fraud is common. I3: bounded by the $25k approval limit and monthly detection (worst credible case $100k–500k over a month). | L2: the compensating review operated 6 of 6 months, plus callbacks. I3. | L2. I3: accepted with the compensating control until the roles are split.
RISK-014 | Unauthorized or untested changes cause an outage or security regression | An emergency or console change is made without review and introduces an outage or exposure (FIND-012 is a realized example). | WCP production configuration | Human error under time pressure; unreviewed emergency changes | Emergency and console change paths lack enforced approval and revert | PR review and CI for code and IaC; protected deploy environments | 3 | 4 |  |  | 2 | 4 |  |  | Mitigate | Retro-approval automation; console-change alerts (POAM-018) | Tomasz Wierzbicki (Director, Platform Engineering) | 2026-09-11 | 2 | 3 |  |  | Treatment in progress (overdue) | CM-3 | FIND-018 | POAM-018 | 2026-09-18 | L3: frequent changes. I4: multi-hour outage or exposure. | L2: 22 of 25 sampled changes were compliant; the pipeline is strong. I4: realized once (FIND-012). | L2. I3: console-change alerting and auto-revert shorten the exposure window.
RISK-015 | Phishing and social engineering of the workforce | A user is tricked into disclosing credentials, approving a push, or sending PHI or payments to an attacker. | Workforce identities and endpoints | Phishing, help-desk social engineering, BEC | 9% training non-completion (at fieldwork); human error | MFA with number challenge; email security; phishing simulations (4.3% click rate); help-desk identity verification; EDR | 5 | 4 |  |  | 3 | 3 |  |  | Accept | Training enforcement (POAM-019); continue simulations and phishing-resistant MFA rollout | Denise Yamamoto (Director of People) | 2026-09-30 | 3 | 3 |  |  | Accepted within tolerance (monitor) | AT-2; AT-3; IA-2(8) | FIND-019 | POAM-019 | 2026-09-18 | L5: phishing attempts are constant. I4: credential compromise leading to PHI access. | L3: layered controls (MFA, filtering, EDR) catch most attempts (INC-2026-0012 shows MFA blocked a successful phish). I3: least privilege and monitoring limit impact. | L3 and I3 unchanged: training completion is a hygiene fix and does not move the risk. Accepted as within tolerance (Moderate) with an ongoing awareness program.
RISK-016 | Loss of SHCA contract or customer trust from unresolved compliance gaps | SHCA or Lakemont judges Wrenfield's remediation insufficient, delaying go-live or leading to termination or non-renewal. | SHCA C3P contract ($23.4M) and top customer relationships (Lakemont) | Contract cure notice or termination; customer non-renewal after security review | Outdated SSP; open High POA&M items near go-live; vendor conditions unmet | This assessment and the POA&M; executive sponsorship; customer communication plan | 3 | 5 |  |  | 3 | 4 |  |  | Mitigate | Close High POA&M items before go-live; SSP rewrite (POAM-017); proactive customer update | Elena Marsh (CEO) | 2026-12-15 | 2 | 3 |  |  | Treatment in progress | PL-2; CA-5; CA-7 | FIND-017 | POAM-017 | 2026-09-18 | L3: 7 High findings against a 90-day rule. I5: loss of a $23.4M contract or a customer worth 21% of ARR. | L3: strong remediation momentum (7 of 19 closed in 6 weeks), but 3 High items are open with dependencies. I4: SHCA would more likely require a cure plan than terminate. | L2: High items closed before 2027-01-11, and the SSP is accurate. I3.
RISK-017 | Service-account credential theft | A stolen long-lived service credential grants quiet, unmonitored access to PHI extracts. | Non-human accounts with static credentials (SFTP push, reporting ETL, vendor logins) | Credential theft from hosts or repositories; vendor-side compromise | Keys 1.5–3 years old; no owners; a shared vendor login | Secrets Manager rotation for DB credentials; OIDC for CI/CD | 3 | 4 |  |  | 3 | 4 |  |  | Mitigate | Owners, rotation or federation, and named vendor accounts (POAM-005) | Alicia Moreno (CISO) | 2026-09-12 | 1 | 4 |  |  | Treated (residual achieved; monitoring) | IA-5; AC-2 | FIND-005 | POAM-005 | 2026-09-18 | L3: static keys leak through repositories, hosts, and backups. I4: PHI extract access. | L3: modern patterns exist, but the legacy exceptions carry the risk. I4. | L1: federation and rotation with owners and quarterly attestation. I4: a compromised service identity would still reach the same data.
RISK-018 | Loss or theft of an endpoint containing PHI | A lost or stolen laptop exposes PHI stored locally. | About 362 workforce laptops | Theft, loss in transit | Mobile workforce (60% remote) | Full-disk encryption (100%); MDM remote wipe; policy against storing PHI locally, with DLP; EDR | 4 | 3 |  |  | 2 | 2 |  |  | Accept | None beyond current controls; annual review | Kevin Brandt (IT Manager) | 2027-07-15 | 2 | 2 |  |  | Accepted within appetite (Low) | SC-28; MP-6 |  |  | 2026-09-18 | L4: several devices are lost each year. I3: a local PHI cache could hold under 500 records. | L2: devices are still lost (INC-2026-0063), but FDE means a lost encrypted device is not a breach of unsecured PHI. I2: exposure is internal-only and non-reportable when encryption is verified. | Unchanged; within appetite.