## README
GRC Templates (blank, with one example row each)
Wrenfield Health (fictional) · simulated NIST SP 800-53 Rev. 5 (Release 5.2.0) assessment · synthetic data
As-of (status) date | 2026-09-18 | <- input: all aging/overdue formulas reference this cell (use =TODAY() in a live workbook)
How to use | Each sheet is a blank template with the same columns as the populated artifact. Row 2 is an EXAMPLE drawn from the Wrenfield sample; delete it before use
Controlled values | Use the vocabularies documented in docs/id-scheme.md and docs/assessment/nist-800-53-strategy.md §5
Populated examples | See controls/, risk/, access-review/, audit/, findings/, poam/, vendor-risk/

## control-matrix
Control ID | Control Family | Control Name | Baseline (SP 800-53B) | Control Requirement Summary | Applicability | Applicability Rationale | Control Origination | System / Process | Control Owner | Business Requirements (REQ) | Implementation Status (Owner-Stated) | Implementation Status (Assessor-Validated) | Status Changed by Assessor? | Implementation Description | Evidence Required | Evidence Available (EVID) | Evidence Location | Highest Evidence Level | Testing Method | Test Procedure / Expected vs Actual | Assessment Result | Gap Identified | Risk Rating | Related Risk ID | Related Finding ID | Related POA&M ID | POA&M Status (as of status date) | Observations | Last Reviewed | Next Review | CSF 2.0 Function (informal) | Notes
AC-2(3) | AC - Access Control | Disable Accounts | Moderate | Disable accounts within a defined period when they have expired, are no longer associated with a user or function, violate policy, or have been inactive for a defined period. | Applicable |  | Hybrid | SYS-01, SYS-02, SYS-03, SYS-07, SYS-09 | Nadia Rahman (IAM Engineer) | REQ-004; REQ-013 | Implemented | Partially Implemented | Yes | ACP-002 §5.3 requires disabling within 24 hours of termination, and §5.6 requires disabling after 90 days of inactivity. IT deactivates Okta accounts from manual tickets. There was no inactivity automation and no process for local accounts. | Complete population of terminations in the period; de-provisioning logs for every system; inactivity report | EVID-003; EVID-004; EVID-007; EVID-061; EVID-062; EVID-064 | evidence/AC/EVID-003_peoplehub-terminations-2026H1.csv; evidence/AC/EVID-004_okta-deactivation-events-2026H1.csv; evidence/IA/EVID-007_aws-iam-credential-report_2026-06-30.csv; evidence/AC/EVID-061_terminations-and-deactivations_2026-07-01_to_09-09.csv; evidence/AC/EVID-062_hr-okta-reconciliation-job_2026-09-10.csv; evidence/IA/EVID-064_aws-iam-credential-report_2026-09-04.csv | Operating Effectiveness | Examine, Test | Re-performed the 24h test on all 19 H1 terminations (docs/assessment/test-results/termination-deprovisioning.md). Expected: 19 of 19 within 24h, including non-SSO accounts. Actual: 16 of 19 within SLA, 1 late (209h), 2 never deactivated (one with a post-termination sign-in, which became INC-2026-0117), plus 1 active local AWS IAM user and 1 Quarrystone portal account belonging to leavers. Validation re-test (2026-09-10): 7 of 7 within SLA, and the reconciliation job reported 0 exceptions. | Other Than Satisfied | De-provisioning depended on manual tickets and missed local accounts. | High | RISK-002 | FIND-001 | POAM-001 | POAM-001: Closed |  | 2026-09-10 | 2027-07-15 | PR | Remediation validated 2026-09-10. Full re-test at the FY27 assessment because the post-fix operating sample is small (7).

## risk-register
Risk ID | Risk Title | Risk Description | Asset / Process | Threat | Vulnerability | Existing Controls | Inherent Likelihood | Inherent Impact | Inherent Score | Inherent Risk | Current Likelihood | Current Impact | Current Score | Current Risk | Treatment Strategy | Planned Mitigation | Risk Owner | Target Date | Residual Likelihood | Residual Impact | Residual Score | Residual Risk | Status | Related NIST Controls | Related Findings | Related POA&M | Review Date | Rationale: Inherent | Rationale: Current | Rationale: Residual
RISK-003 | Account takeover through MFA gaps | An attacker obtains the password of an MFA-exempt account and signs in directly, inheriting that user's access, including identity administration. | Okta and all federated systems | Credential phishing, password spraying, reuse of breached credentials | MFA exemption group (9 humans incl. an Okta Super Admin); IAM user without MFA | Global MFA policy for 97% of users; replay-resistant authenticators; Okta ThreatInsight | 4 | 5 | 20 | Critical | 3 | 5 | 15 | High | Mitigate | Delete the exemption policy; enroll all users; phishing-resistant admin MFA; exception workflow (POAM-002) | Alicia Moreno (CISO) | 2026-09-05 | 2 | 4 | 8 | Moderate | Treated (residual achieved; monitoring) | IA-2(1); IA-2(2); IA-2(8) | FIND-002 | POAM-002 | 2026-09-18 | L4: phishing is the leading initial-access vector. I5: federation reaches AWS prod and PHI. | L3: MFA covers 97%, a partial control. I5: an exempt Okta Super Admin could reach everything. | L2: no exemptions; phishing-resistant MFA for admins; token theft still possible. I4: least-privilege work narrows what one account reaches.

## access-review
Row ID | User / Account | Account Type | Department | Role | Manager | HR Status | System | Access Level | Privileged? | PHI Access? | Date Granted | Last Login | Business Justification | Reviewer | Review Date | Engine Flags | Review Decision | Exception ID | Issue Identified | Required Action | Action Owner | Due Date | Completion Status | Completion Date | Closure Evidence | Related Finding | Affected Control | Reviewer Comment
ENT-058 | mfeld-admin | IAM user (local) | Platform Engineering | DevOps Engineer | Tomasz Wierzbicki | Terminated | AWS wcp-prod | AdministratorAccess | Y | Y | 2021-09-20 | 2026-03-20 | Legacy IAM user created before IAM Identity Center rollout | Tomasz Wierzbicki | 2026-07-06 | F-DAILYADMIN; F-INACTIVE; F-TERM | Revoke | AR-EX-03 | Local AWS IAM user of employee terminated 2026-03-27 still active (console password + access key); outside Okta de-provisioning | Delete IAM user and keys; review CloudTrail for activity after 2026-03-27 | Tomasz Wierzbicki | 2026-07-07 | Completed | 2026-07-06 | EVID-064 | FIND-001 | AC-2(3); AC-2 | CloudTrail shows no use after 2026-03-20; root cause is local accounts outside SSO

## evidence-tracker
Evidence ID | Control ID | Evidence Request | Artifact Description | Evidence Owner | Request Date | Due Date | Received Date | Status | Evidence Period | File / Repository Location | In Repo? | Reviewer | Review Result | Evidence Level | Sufficiency | Exception | Follow-Up Required | Days Late | Notes
EVID-003 | AC-2(3); PS-4 | System-generated list of ALL terminations 2026-01-01 to 2026-06-30 (worker ID, type, date, effective time) | PeopleHub report 'Terminations by Effective Date' + final-pay reconciliation | Denise Yamamoto | 2026-06-10 | 2026-06-19 | 2026-06-17 | Accepted | 2026-01-01 to 2026-06-30 | evidence/AC/EVID-003_peoplehub-terminations-2026H1.csv | Yes | Lead assessor | IPE validated: 19 of 19 reconciled to final pay/invoice | Operating Effectiveness | Sufficient |  | No | 0 | Assessor observed report generation over screen share

## findings-register
Finding ID | Title | Severity | Likelihood | Impact | Score | Primary Control | Related Controls | Related Risks | POA&M ID | Source | Related Items (AR-EX / VR / EVID) | Date Identified | Owner | Status | Condition | Criteria | Cause | Effect | Recommendation | Management Response | Challenge Record
FIND-002 | MFA not enforced for all workforce and privileged accounts | High | 4 | 4 | 16 | IA-2(1) | IA-2(1); IA-2(2) | RISK-003 | POAM-002 | Control test + access review | AR-EX-11; EVID-010; EVID-011; EVID-007; EVID-063; EVID-064 | 2026-06-30 | Nadia Rahman (IAM Engineer) | Closed | An Okta policy created in 2023 as a "temporary" workaround exempted the MFA-Exempt-Legacy group (11 accounts, 9 human) from MFA. One member was an Okta Super Administrator. None of the exemptions had approval or an expiry date. In AWS, the IAM user mfeld-admin (AdministratorAccess) had a console password and no MFA. | SHCA CSA §3.2 requires MFA for all privileged and remote access. HIPAA 164.312(d) requires person or entity authentication. ACP-002 §6.1 limits exceptions to 30 days with CISO approval. | Exceptions were granted by help desk and IT without a workflow, an expiry, or review. Legacy IAM users bypass the Okta policy entirely. | Password-only access to an identity administrator account put every downstream system at risk from a single phished password. This is the exact MFA concern raised in the Lakemont review. | Remove the exemption policy and group. Enroll all members, with accommodation alternatives such as hardware keys. Convert service users to non-interactive integrations. Require phishing-resistant MFA for admin apps. Remove IAM users other than break-glass. Implement a time-bound exception workflow. | Agree. Target 2026-09-05.

## poam
POA&M ID | Related Finding | Related Control | Related Risk | Weakness | Root Cause | Severity | Corrective Action | Milestones | Owner | Resources Required | Open Date | SLA Date | Original Target Date | Current Target Date | Target Change Reason | Current Status | Percent Complete | Days Open | Overdue? | Slipped? | Target Within SLA? | Dependencies | Validation Method | Closure Evidence | Validated By | Closure Date | Residual Risk | Notes
POAM-013 | FIND-013 | CP-9(1) | RISK-008 | Backup restoration never tested | Recoverability assumed from job success; no scheduled restore test | Moderate | Documented restore from DR vault into isolated account with timing and integrity checks; semi-annual schedule in BCP-003 | M1 Write restore runbook and integrity-check queries (due 2026-08-21; Done) ¦ M2 Perform restore test (assessor observes) (due 2026-08-28; Done) ¦ M3 Add semi-annual restore test to BCP-003 calendar; assessor validation (due 2026-09-01; Done) | Tomasz Wierzbicki (Director, Platform Engineering) | SRE (about 16h); isolated recovery account | 2026-08-07 | 2027-02-03 | 2026-09-01 | 2026-09-01 |  | Closed | 1 | 25 | No | No | Yes |  | Observation of restore test; inspection of timings vs RTO/RPO and integrity check output | EVID-069 | Lead assessor | 2026-09-01 | Moderate (RISK-008 residual L2 x I4 = 8, pending POAM-014)

## vendor-assessment
Question ID | Security Domain | Requirement | Vendor Response | Evidence | Assessor Evaluation | Risk Identified | Severity | Recommendation | Owner | Status | Vendor Finding
VQ-16 | Breach notification | Notify Wrenfield of security incidents affecting its data within 24 hours of discovery | BAA: 'without unreasonable delay and no later than 30 days' | BAA §4.2 | Unsatisfactory | Breach notification term of 30 days | High | Amend BAA to 24h notice of suspected or confirmed incidents affecting Wrenfield data, with defined content and updates | Theo Anand (General Counsel) | In negotiation (redline v3) | VR-002

## vendor-inventory
Vendor ID | Vendor | Service | Business Owner | Data Sensitivity (0-3) | Data Volume (0-3) | Access / Integration (0-3) | Business Criticality (0-3) | Substitutability (0-2) | Inherent Score | Tier | Last Assessed | Reassess (months) | Next Due | Assessment Current? | Assessment Method | Breach Notice Term | Fourth Parties Mapped? | Real Platform?
VEN-004 | Quarrystone Analytics, LLC (fictional) | Population-health analytics; nightly full-PHI extract (about 410k patients) | Miriam Castell | 3 | 3 | 2 | 2 | 2 | 12 | 1 | 2026-07-24 | 12 | 2027-07-24 | Yes | Deep assessment (this engagement): questionnaire, SOC 2 review, interviews | 30 days (BAA 2023) | Yes (4 subprocessors identified during this assessment) | No (fictional)